## Cabinet List
Category | ERP Projects | Description | Update | Status | Target Date | Priority | Complexity | Source | % Complete
1. Enrollment | Colleague - Registration Triage | Implement improvements to Self Service Interface | Recommended configuration changes and welcome letters have been completed | 1. In Progress | 2020-09-01 | 2. High | 4. Medium | Cabinet | 95%
1. Enrollment | Colleague - Student Planning | Implement Colleague Student Planning - Phase 1: electronic ed plans for counselors | Student Planning has been released to the pilot counselors, feedback on-going, creating more tracks | 1. In Progress | 2020-12-01 | 2. High | 1. Very Large | TCC | 95%
1. Enrollment | Colleague - Registration Upgrade | Implement Colleague Self Service/Registration | Initial configuration begun; Background coding of rosters in Test | 1. In Progress | 2020-12-01 | 2. High | 1. Very Large | TCC | 85%
1. Enrollment | Colleague - Custom Sort Sections | Sort sections by time of day | Confirmed Ellucian will include in September update; Preparing new update in Test | 1. In Progress | 2020-09-01 | 2. High | 1. Very Large | Cabinet | 0%
1. Enrollment | Colleague - Financial Aid | Implement Colleague Financial Aid | CA State Grant Interface built; Postponed indefinitely | 2. On Hold | N/A | 2. High | 1. Very Large | TCC | 0%
1. Enrollment | Colleague - CRM Recruit Phase II | Route CCCApply data through CRM Recruit and configure for students (includes increasing frequency of application uploads) | Test authentication path built with CCC Tech Center; Recruit/Admissions BPA occurring 8/31 - 9/3 | 1. In Progress | 2020-10-01 | 3. Medium | 1. Very Large | TCC | 75%
1. Enrollment | Colleague - Optimization (Cohort Coding) | Create new value codes in the cohort screen and/or student type field (dual enrollment, FYE, incarcerated students) | Recommendations have been developed; Meeting with Instructional Ops on 6/1 | 1. In Progress | 2020-10-31 | 3. Medium | 3. Med-Large | TCC | 60%
1. Enrollment | Colleague - Transition WA links to Self Service | Transition links and custom programs from WebAdvisor to Self Service (July 2021) | After faculty rosters transition, then begin with student billing links (e.g., Nelnet) | 1. In Progress | 2021-06-30 | 3. Medium | 3. Med-Large | TCC | 5%
1. Enrollment | Colleague - Drop Reason Codes | Program and define drop reason codes in Colleague | Drop reasons have been initiated for COVID-19; further codes will be developed for future term | 1. In Progress | N/A | 4. Low | 6. Small | TAC | 0%
1. Enrollment | Colleague - Degree Audit | Implement Colleague Degree Audit (Student Planning: Phase II) | Audit of Degree Audit complete; Decision needs to be made | 3. Not Started | N/A | 5. Unknown | 1. Very Large | TCC | 0%
2. Compliance | Colleague - AB2248 | Notify Cal Grant students of full-time status and collect receipt of that notification | Engaged with FA re: wording; Need college approval of process | 1. In Progress | 2020-09-01 | 1. Critical | 6. Small | TAC | 75%
2. Compliance | Colleague - SAM Integration with Student Billing | Build integration between SAM and Colleague for detailed posting to student accounts | Need to finish transition to Linux first; Building SOW based on specs identified by DOE auditors | 3. Not Started | 2020-12-31 | 2. High | 4. Medium | FA Audit | 0%
2. Compliance | Colleague - Optimization (Student Finance) | Redo GL accounts to itemize student billing | Engagements have begun in Accounting; More engagements week of 6/1 | 1. In Progress | 2020-12-01 | 3. Medium | 2. Large | TCC | 25%
2. Compliance | Maxient | Software to track Title IX claims/actions | SSO completed; Kickoff meeting completed; Project implementation postponed due to COVID-19 | 2. On Hold | 2020-12-01 | 3. Medium | 4. Medium | TCC | 20%
2. Compliance | Colleague - Directory Opt Out/FERPA Notifications | Implement Directory Opt Out/FERPA notifications in Self Service | Can use Self Service functionality (e.g., AB2248) | 3. Not Started | 2020-09-01 | 5. Unknown | 6. Small | TAC | 50%
2. Compliance | Closed Captioning | ? | Needs SOW & Prioritization | 3. Not Started | N/A | 5. Unknown | 8. Unknown | SS RRT | 0%
3. Infrastructure | Colleague - UI upgrade to version 5.X | Upgrade Colleague UI to version 5.x (older version not supported) | Colleague UI 5.X installed and ImageNow users are all using the new interface | 1. In Progress | 2020-12-01 | 1. Critical | 3. Med-Large | Operational | 90%
3. Infrastructure | Microsoft - Office 365 SSO | Implement single sign on and Office 365 for students (accounts in the cloud) | Student accounts in the cloud; Migrated viral student accounts; Students accounts creation process complete; Need to decide policies and communication plan | 1. In Progress | 2020-09-30 | 2. High | 1. Very Large | Tech RRT | 80%
3. Infrastructure | Canvas - SSO for Students | Implement SSO for students | Dependent on Office 365 SSO | 3. Not Started | N/A | 2. High | 5. Sm-Medium | Tech RRT | 0%
3. Infrastructure | Colleague - SSO for Students | Implement SSO for students | Dependent on Office 365 SSO | 3. Not Started | N/A | 2. High | 2. Large | Tech RRT | 0%
3. Infrastructure | Curriculum Management Software | Implement curriculum management software districtwide | Waiting to see conclusion of CCCCO RFP | 3. Not Started | N/A | 2. High | 1. Very Large | TCC | 0%
3. Infrastructure | Website Redesign (Colleges) | Regional Workforce project to redesign GCCCD websites | College websites are live; Working through issues | 1. In Progress | 2020-08-01 | 3. Medium | 2. Large | Cabinet | 90%
3. Infrastructure | Colleague - Optimization (Communication Management) | Optimize the use of Colleague communication management process | AB19 communication process done; Engagements scheduled for Feb 24-26 & Mar 17-18 | 1. In Progress | 2020-09-01 | 3. Medium | 6. Small | TCC | 50%
3. Infrastructure | SAM - Transition to Linux server | Transition SAM to Linux from Unix | Licensing issue with Microfocus resolved; PR routing through process | 1. In Progress | 2020-10-01 | 3. Medium | 4. Medium | Operational | 50%
3. Infrastructure | Colleague - SQL Transition | Convert Colleague databases to a SQL environment | Data cleaning and documentation in process; Documenting customizations | 1. In Progress | 2020-10-31 | 3. Medium | 1. Very Large | TCC | 40%
3. Infrastructure | Colleague - Optimization (Student Addresses) | Optimize the way Colleague uses addresses | Engagement scheduled March 9-10; Further work needed from A&R | 1. In Progress | 2020-12-01 | 3. Medium | 6. Small | TCC | 25%
3. Infrastructure | Adobe - AdobeSign | Implement eSignatures and forms districtwide | Pending discovery and comparison with other tools | 3. Not Started | N/A | 3. Medium | 3. Med-Large | Tech RRT | 0%
3. Infrastructure | Credentials - eTranscripts | Set up Credentials for remote processing and delivery of eTranscripts | In final stages of identifying fee structure for students. | 1. In Progress | 2020-09-30 | 3. Medium | 6. Small | SS RRT | 0%
3. Infrastructure | Website Redesign (District) | Convert District website to OU Campus | Need project plan and procurement for configuration services | 3. Not Started | N/A | 3. Medium | 3. Med-Large | Cabinet | 0%
3. Infrastructure | iFAS transition and removal | Transition all data from iFAS into SQL database | IT has begun constructing SQL database to house data | 1. In Progress | 2020-12-31 | 4. Low | 3. Med-Large | Operational | 60%
3. Infrastructure | 25Live - HVAC Integration | Integrate HVAC controls with room scheduling software | Server built; Pilot of 23 rooms; Project on hold until Loren comes back from leave | 2. On Hold | N/A | 4. Low | 7. Very Small | Operational | 50%
3. Infrastructure | Cynosure - "De-Linking" Orientation & Advising | Delink orientation from advising modules for CC | Need to prioritize SOW | 3. Not Started | N/A | 5. Unknown | 5. Sm-Medium | TAC | 0%
3. Infrastructure | Campus Logic - Financial Aid Document Processing | Implement Campus Logic for Financial Aid document processing | Needs SOW & Prioritization | 3. Not Started | N/A | 5. Unknown | 8. Unknown | SS RRT | 0%
3. Infrastructure | Comevo Orientation Software | Implement Comevo orientation software for CC | Needs SOW & Prioritization | 3. Not Started | N/A | 5. Unknown | 3. Med-Large | SS RRT | 0%
4. Strategic Plan | Colleague - Demo CRM Advise | Demo Colleague student success/retention module | Demo scheduled for Jan 22; Need to schedule another personalized demo later in Spring | 2. On Hold | N/A | 3. Medium | 7. Very Small | TCC | 75%
4. Strategic Plan | GUHSD-GCCCD Database | Develop GUHSD-GCCCD database to house CALPADS files and match with Colleague data | Received the 2018-19 data, created SQL tables; Requested additional years from GUHSD (9/1) | 1. In Progress | 2020-12-31 | 3. Medium | 2. Large | Alliance SC | 25%
4. Strategic Plan | Colleague - Manage Student Programs (Optimization) | Get the majors stored in Colleague to represent a student’s true major/program | Will roll into optimization work; Could be affected by Degree Audit implementation | 3. Not Started | N/A | 3. Medium | 4. Medium | TCC | 0%
4. Strategic Plan | DARs Degree Audit | DARS Degree Audit for Students | On hold, pending review of Colleague Degree Audit | 2. On Hold | N/A | 4. Low | 8. Unknown | On Prior List | 0%
4. Strategic Plan | CCC MyPath | Create API to connect to the application for career/major coaching | Needs SOW & Prioritization | 3. Not Started | N/A | 5. Unknown | 8. Unknown | SESC | 0%
4. Strategic Plan | SARs - Early Alert | Implement Early Alert system | Needs SOW & Prioritization | 3. Not Started | N/A | 5. Unknown | 8. Unknown | SS RRT | 0%
5. Improvements | Workday - AdobeSign | Implement AdobeSign integration with Workday for Recruiting/Onboarding | IT functionality complete; HR testing: Need approval to buy District licenses | 1. In Progress | 2020-09-30 | 3. Medium | 6. Small | Workday SC | 90%
5. Improvements | Colleague - B&N API | Barnes & Noble integration with Colleague | Need to complete SOW; Product changed, assessing new capability | 3. Not Started | 2020-12-01 | 4. Low | 6. Small | On Prior List | 0%
5. Improvements | Colleague - Ellucian Mobile | Colleague mobile application for students | Colleague mobile application for students (dependency on Colleague Financial Aid and Self Service build out) | 3. Not Started | Sum 2021 | 4. Low | 8. Unknown | TCC | 0%
5. Improvements | Sharepoint | Implement Sharepoint for depts, committees, etc | On hold, may use new CMS instead | 3. Not Started | N/A | 4. Low | 1. Very Large | On Prior List | 0%
5. Improvements | Workday - Mobile | Workday Mobile application for employees and prospective employees | Need to discover security aspects to mobile - will look at this after VoIP | 3. Not Started | N/A | 4. Low | 6. Small | Workday SC | 0%
5. Improvements | Workday - P-cards | Re-engineer the procurement card process and implement in Workday | Might cancel this project | 3. Not Started | N/A | 4. Low | 8. Unknown | Workday SC | 0%
5. Improvements | Workday - Purchasing "Punchouts" | Implement purchasing pre-set "punchouts" for select vendors (e.g., Dell) in Workday | Need project plan | 3. Not Started | N/A | 4. Low | 6. Small | Workday SC | 0%
5. Improvements | 25Live - CollegeNet | Implement CollegeNet product from 25Live | Needs SOW & Prioritization | 3. Not Started | N/A | 5. Unknown | 8. Unknown | SS RRT | 0%
5. Improvements | One Card System | ID Card, Access control, student services | Needs SOW & Prioritization | 3. Not Started | N/A | 5. Unknown | 8. Unknown | SS RRT | 0%
5. Improvements | SARs - Waitlisting | Implement SARs waitlisting module | Needs SOW & Prioritization | 3. Not Started | N/A | 5. Unknown | 8. Unknown | SS RRT | 0%
5. Improvements | Telehealth System | Implement Telehealth system | Needs SOW & Prioritization | 3. Not Started | N/A | 5. Unknown | 8. Unknown | SS RRT | 0%
5. Improvements | ImageNow - Web Scanning | Implement web scanning module from ImageNow | Needs SOW & Prioritization | 3. Not Started | N/A | 5. Unknown | 8. Unknown | SS RRT | 0%
5. Improvements | ImageNow - Perceptive Content | Implement upgraded cloud-based Perceptive Experience product | Needs SOW and prioritization | 3. Not Started | N/A | 5. Unknown | 2. Large | SS RRT | 0%
Category | Technical Infrastructure Projects | Description | Update | Status | Target Date | Priority | Complexity |  | % Complete
3. Infrastructure | Building - GC PVAC | Install and configure switches, WAPs, cabling, ports, and phones for PVAC | Project almost complete; IT will still need to take care of little projects here and there. | 1. In Progress | 2020-09-01 | 1. Critical | 4. Medium | Facilities MP | 100%
3. Infrastructure | Dell - Backup System | Install new backup servers/system | Equipment installed at GC - CC; Vendor and IT engaged in setup. | 1. In Progress | 2020-09-15 | 1. Critical | 2. Large | Tech Plan | 100%
3. Infrastructure | Building - CC Student Services | Plan IT infrastructure for CC Student Services Building | Meetings are ongoing | 1. In Progress | 2020-12-20 | 1. Critical | 4. Medium | Facilities MP | 0%
3. Infrastructure | Building - GC Building 36 | Install and configure switches, WAPs, cabling, ports, and phones for Building 36 | Not Started - We need to wait until the building is ready before we can do this | 1. In Progress | 2020-12-20 | 1. Critical | 4. Medium | Facilities MP | 10%
3. Infrastructure | VM Ware Expansion | Expand VMware at Cuyamaca; PR for VMware and servers processed. | Need to expand VM environment for disaster recovery of backup tapes districtwide. | 1. In Progress | 2020-12-20 | 1. Critical | 6. Small | Operational | 90%
3. Infrastructure | Microsoft - Windows Virtual Desktop | Set up and pilot the MS Windows virtual desktop environment for remote access | VDs installed; Developing "golden image"; MS needs to provide new update in order to configure support options | 1. In Progress | 2020-09-30 | 2. High | 2. Large | Tech RRT | 90%
3. Infrastructure | VoIP - Softphone Feature Rollout | Implement the Mitel Softphone feature for remote calling functionality | Softphones are rolling out to the campus community, starting with departments with student-facing services | 1. In Progress | 2020-08-31 | 2. High | 5. Sm-Medium | Tech RRT | 50%
3. Infrastructure | Building - Outdoor WiFi | Install WAPs in high-use outside areas (e.g., GC Quad, CC Student Center, etc.) | Project is now in process; Identifying scope, including parking lots at GC-CC; Temporary solution scheduled for installation the week of 9/14 | 1. In Progress | 2021-03-01 | 2. High | 5. Sm-Medium | TCC | 33%
3. Infrastructure | Cloud Backup System | Transition from tape backups to offsite cloud backups | After our new backup setup is purchased and completed, we need to begin work on moving our tape backups to the cloud. | 3. Not Started | 2020-12-31 | 2. High | 2. Large | Tech Plan | 0%
3. Infrastructure | Microsoft - Windows 10 Image | Create new Windows 10 image (Nov 2019) and implement Office 2019 | In order to stay secure and updated on Windows 10 we need to create another image based on last Novembers release; Networking team actively working on this project | 1. In Progress | 2020-08-31 | 2. High | 4. Medium | Operational | 100%
3. Infrastructure | Microsoft - Teams | Implement MS Teams as a collaborative tools for employees | IT is researching solution. | 1. In Progress | 2020-12-31 | 3. Medium | 5. Sm-Medium | Tech RRT | 10%
3. Infrastructure | UPS Installation | Install backup power for all switches districtwide | The colleges have requested that we install UPS systems in all of our MDF/IDF closets that support phones--need to document all closets. | 3. Not Started | 2021-12-31 | 3. Medium | 1. Very Large | Tech Plan | 0%
3. Infrastructure | Microsoft - Student Tenant | Create Office365 Student Accounts | O365 "viral" student tenant has been migrated over to GCCCD | 4. Completed | 2020-08-17 | 4. Low | 7. Very Small | Tech RRT | 100%
5. Improvements | Palo Alto - Internal Firewall | Install internal firewall and replace text-based access control list | We will modernize our internal security by getting rid of our text based access control lists and moving to a dynamic Palo Alto Firewall. | 1. In Progress | 2020-12-31 | 3. Medium | 2. Large | Security Plan | 20%
5. Improvements | Active Directory Cleanup | Clean up active directory of all unused accounts and create process for employee terminations/position changes | This is a security risk after years of neglect. | 3. Not Started | 2020-12-20 | 3. Medium | 4. Medium | Operational | 0%
5. Improvements | Workspace One - Mobile Device Management | GC ICS has requested this software to manage mobile devices | We are now investigating Microsoft Endpoint Management for remote devices. | 3. Not Started | 2020-12-31 | 3. Medium | 6. Small | Tech RRT | 10%
Formulas:
Target Date = IFERROR(VLOOKUP([ERP Projects],'ERP Full List'!$B2:P84,5, FALSE),"")
Target Date = VLOOKUP([ERP Projects],'Infrastructure List'!$B2:P70,5,FALSE)

## ERP Full List
System | Project | Description | Update | Status | Target Date | Category | Priority | Complexity | % Complete | Source | Dependency | Resource 1 | Resource 2 | Resource 3 | Resource 4
Colleague | Colleague - Custom Sort Sections | Sort sections by time of day | Confirmed Ellucian will include in September update; Preparing new update in Test | 1. In Progress | 2020-12-31 | 1. Enrollment | 2. High | 1. Very Large | 0% | Cabinet |  | Mark Chan | Eric Lane (c) | Laura Murphey
Colleague | Colleague - Registration Upgrade | Implement Colleague Self Service/Registration | Initial configuration begun; Background coding of rosters in Test | 1. In Progress | 2020-12-31 | 1. Enrollment | 2. High | 1. Very Large | 85% | TCC |  | Eric Lane (c) | Laura Murphey | Mark Chan
Colleague | Colleague - Registration Triage | Implement improvements to Self Service Interface | Recommended configuration changes and welcome letters have been completed | 1. In Progress | 2020-06-30 | 1. Enrollment | 2. High | 4. Medium | 95% | Cabinet |  | Eric Lane (c) | Laura Murphey | Mark Chan
Colleague | Colleague - Student Planning | Implement Colleague Student Planning - Phase 1: electronic ed plans for counselors | Student Planning has been released to the pilot counselors, feedback on-going, creating more tracks | 1. In Progress | 2020-04-01 | 1. Enrollment | 2. High | 1. Very Large | 95% | TCC |  | Shari Waters (c) | Eric Lane (c) | Laura Murphey
Colleague | Colleague - Transition WA links to Self Service | Transition links and custom programs from WebAdvisor to Self Service (July 2021) | After faculty rosters transition, then begin with student billing links (e.g., Nelnet) | 1. In Progress | 2021-06-30 | 1. Enrollment | 3. Medium | 3. Med-Large | 5% | TCC |  | Brian Nath (c) | Richard Beres (c) | Jim Dorris | Mark Chan
Colleague | Colleague - Optimization (Cohort Coding) | Create new value codes in the cohort screen and/or student type field (dual enrollment, FYE, incarcerated students) | Recommendations have been developed; Meeting with Instructional Ops on 6/1 | 1. In Progress | 2020-10-31 | 1. Enrollment | 3. Medium | 3. Med-Large | 60% | TCC |  | Shari Waters (c) | Mark Chan | Laura Murphey | Joan Bowen (c)
Colleague | Colleague - CRM Recruit Phase II | Route CCCApply data through CRM Recruit and configure for students (includes increasing frequency of application uploads) | Test authentication path built with CCC Tech Center; Recruit/Admissions BPA occurring 8/31 - 9/3 | 1. In Progress | 2020-12-31 | 1. Enrollment | 3. Medium | 1. Very Large | 75% | TCC |  | Shari Waters (c) | Mark Chan | Laura Murphey | John Saric
Colleague | Colleague - Drop Reason Codes | Program and define drop reason codes in Colleague | Drop reasons have been initiated for COVID-19; further codes will be developed for future term | 1. In Progress | 2020-12-31 | 1. Enrollment | 4. Low | 6. Small | 90% | TAC |  | Eric Lane (c) | Laura Murphey
Colleague | Colleague - AB2248 | Notify Cal Grant students of full-time status and collect receipt of that notification | Engaged with FA re: wording; Need college approval of process | 1. In Progress | 2020-09-30 | 2. Compliance | 1. Critical | 6. Small | 75% | TAC |  | Eric Lane (c) | Mark Chan
Colleague | Colleague - Optimization (Student Finance) | Redo GL accounts to itemize student billing | Engagements have begun in Accounting; More engagements week of 6/1 | 1. In Progress | 2020-09-30 | 2. Compliance | 3. Medium | 2. Large | 25% | TCC |  | Shari Waters (c) | Alla Lyukin | Laura Murphey
Colleague | Colleague - UI upgrade to version 5.X | Upgrade Colleague UI to version 5.x (older version not supported) | Colleague UI 5.X installed and ImageNow users are all using the new interface | 1. In Progress | 2020-11-30 | 3. Infrastructure | 1. Critical | 3. Med-Large | 90% | Operational | ImageNow Upgrade | Jim Dorris
Microsoft | Microsoft - Office 365 SSO | Implement single sign on and Office 365 for students (accounts in the cloud) | Student accounts in the cloud; Migrated viral student accounts; Students accounts creation process complete; Need to decide policies and communication plan | 1. In Progress | 2020-09-30 | 3. Infrastructure | 2. High | 1. Very Large | 80% | Tech RRT |  | Steve Abat | Jerry Williamson | Robert Mountain | Brian Nath (c)
Credentials | Credentials - eTranscripts | Set up Credentials for remote processing and delivery of eTranscripts | Amendment to contract routing through purchasing | 1. In Progress | 2020-09-30 | 3. Infrastructure | 3. Medium | 6. Small | 0% | SS RRT
Colleague | Colleague - Optimization (Student Addresses) | Optimize the way Colleague uses addresses | Engagement scheduled March 9-10; Further work needed from A&R | 1. In Progress | 2020-12-31 | 3. Infrastructure | 3. Medium | 6. Small | 25% | TCC |  | Shari Waters (c) | Mark Chan | Laura Murphey
Colleague | Colleague - SQL Transition | Convert Colleague databases to a SQL environment | Data cleaning and documentation in process; Documenting customizations | 1. In Progress | 2020-10-31 | 3. Infrastructure | 3. Medium | 1. Very Large | 40% | TCC |  | Brian Nath (c) | Eric Lane (c) | Richard Beres (c)
Colleague | Colleague - Optimization (Communication Management) | Optimize the use of Colleague communication management process | AB19 communication process done; Engagements scheduled for Feb 24-26 & Mar 17-18 | 1. In Progress | 2020-05-31 | 3. Infrastructure | 3. Medium | 6. Small | 50% | TCC |  | Shari Waters (c) | Mark Chan | Laura Murphey
SAM | SAM - Transition to Linux server | Transition SAM to Linux from Unix | Licensing issue with Microfocus resolved; PR routing through process | 1. In Progress | 2020-09-30 | 3. Infrastructure | 3. Medium | 4. Medium | 50% | Operational
OmniUpdate | Website Redesign (Colleges) | Regional Workforce project to redesign GCCCD websites | College websites are live; Working through issues | 1. In Progress | 2020-08-01 | 3. Infrastructure | 3. Medium | 2. Large | 90% | Cabinet |  | Gabe Neri
iFAS | iFAS Transition and Removal | Transition all data from iFAS into SQL database | IT has begun constructing SQL database to house data | 1. In Progress | 2020-12-31 | 3. Infrastructure | 4. Low | 3. Med-Large | 60% | Operational | Workday - Foundation | Jim Dorris | Richard Beres (c)
Microsoft | GUHSD-GCCCD Database | Develop GUHSD-GCCCD database to house CALPADS files and match with Colleague data | Received the 2018-19 data, created SQL tables; Requested additional years from GUHSD (9/1) | 1. In Progress | 2020-12-31 | 4. Strategic Plan | 3. Medium | 2. Large | 25% | Alliance SC |  | Richard Beres (c) | RPIE
Workday | Workday - AdobeSign | Implement AdobeSign integration with Workday for Recruiting/Onboarding | IT functionality complete; HR testing: Need approval to buy District licenses | 1. In Progress | 2020-09-30 | 5. Improvements | 3. Medium | 6. Small | 90% | Workday SC |  | Shane Stewart
Colleague | Colleague - Financial Aid | Implement Colleague Financial Aid | CA State Grant Interface built; Postponed indefinitely | 2. On Hold | N/A | 1. Enrollment | 2. High | 1. Very Large | 0% | TCC |  | Eric Lane (c) | Mark Chan | John Campbell
Maxient | Maxient | Software to track Title IX claims/actions | SSO completed; Kickoff meeting completed; Project implementation postponed due to COVID-19 | 2. On Hold | 2021-06-30 | 2. Compliance | 3. Medium | 4. Medium | 20% | TCC |  | Asma AbuShadi | Jessica McKean | Richard Beres (c)
25Live | 25Live - HVAC Integration | Integrate HVAC controls with room scheduling software | Server built; Pilot of 23 rooms; Project on hold until Loren comes back from leave | 2. On Hold | N/A | 3. Infrastructure | 4. Low | 7. Very Small | 50% | Operational |  | Steve Abat | Alla Lyukin | Jim Dorris
Colleague | Colleague - Demo CRM Advise | Demo Colleague student success/retention module | Demo scheduled for Jan 22; Need to schedule another personalized demo later in Spring | 2. On Hold | N/A | 4. Strategic Plan | 3. Medium | 7. Very Small | 75% | TCC |  | Shari Waters (c)
DARs | DARs Degree Audit | DARS Degree Audit for Students | On hold, pending review of Colleague Degree Audit | 2. On Hold | N/A | 4. Strategic Plan | 4. Low | 8. Unknown | 0% | On Prior List
Colleague | Colleague - Degree Audit | Implement Colleague Degree Audit (Student Planning: Phase II) | Audit of Degree Audit complete; Decision needs to be made | 3. Not Started | N/A | 1. Enrollment | 5. Unknown | 1. Very Large | 0% | TCC |  | Mark Chan | Laura Murphey | Joan Bowen (c)
Colleague | Colleague - SAM Integration with Student Billing | Build integration between SAM and Colleague for detailed posting to student accounts | Need to finish transition to Linux first; Building SOW based on specs identified by DOE auditors | 3. Not Started | 2020-12-31 | 2. Compliance | 2. High | 4. Medium | 0% | FA Audit | SAM - Transition to Linux server | John Campbell | Shane Stewart
Closed Captioning | Closed Captioning | ? | Needs SOW & Prioritization | 3. Not Started | N/A | 2. Compliance | 5. Unknown | 8. Unknown | 0% | SS RRT
Colleague | Colleague - Directory Opt Out/FERPA Notifications | Implement Directory Opt Out/FERPA notifications in Self Service | Can use Self Service functionality (e.g., AB2248) | 3. Not Started | N/A | 2. Compliance | 5. Unknown | 6. Small | 0% | TAC |  | Mark Chan | Laura Murphey
Canvas | Canvas - SSO for Students | Implement SSO for students | Dependent on Office 365 SSO | 3. Not Started | N/A | 3. Infrastructure | 2. High | 5. Sm-Medium | 0% | Tech RRT | Microsoft - Office 365 SSO
Colleague | Colleague - SSO for Students | Implement SSO for students | Dependent on Office 365 SSO | 3. Not Started | N/A | 3. Infrastructure | 2. High | 2. Large | 0% | Tech RRT | Microsoft - Office 365 SSO
Curriculum | Curriculum Management Software | Implement curriculum management software districtwide | Waiting to see conclusion of CCCCO RFP | 3. Not Started | N/A | 3. Infrastructure | 2. High | 1. Very Large | 0% | TCC |  | Mark Chan | Laura Murphey
Adobe | Adobe - AdobeSign | Implement eSignatures and forms districtwide | Pending discovery and comparison with other tools | 3. Not Started | N/A | 3. Infrastructure | 3. Medium | 3. Med-Large | 0% | Tech RRT |  | Shane Stewart
OmniUpdate | Website Redesign (District) | Convert District website to OU Campus | Need project plan and procurement for configuration services | 3. Not Started | N/A | 3. Infrastructure | 3. Medium | 3. Med-Large | 0% | Cabinet |  | Gabe Neri
Campus Logic | Campus Logic - Financial Aid Document Processing | Implement Campus Logic for Financial Aid document processing | Needs SOW & Prioritization | 3. Not Started | N/A | 3. Infrastructure | 5. Unknown | 8. Unknown | 0% | SS RRT
Comevo | Comevo Orientation Software | Implement Comevo orientation software for CC | Needs SOW & Prioritization | 3. Not Started | N/A | 3. Infrastructure | 5. Unknown | 3. Med-Large | 0% | SS RRT
Cynosure | Cynosure - "De-Linking" Orientation & Advising | Delink orientation from advising modules for CC | Need to prioritize SOW | 3. Not Started | N/A | 3. Infrastructure | 5. Unknown | 5. Sm-Medium | 0% | TAC |  | Frank Moore | Jim Dorris
Colleague | Colleague - Manage Student Programs (Optimization) | Get the majors stored in Colleague to represent a student’s true major/program | Will roll into optimization work; Could be affected by Degree Audit implementation | 3. Not Started | N/A | 4. Strategic Plan | 3. Medium | 4. Medium | 0% | TCC |  | Shari Waters (c) | Eric Lane (c) | Mark Chan | Laura Murphey
MyPath | CCC MyPath | Create API to connect to the application for career/major coaching | Needs SOW & Prioritization | 3. Not Started | N/A | 4. Strategic Plan | 5. Unknown | 8. Unknown | 0% | SESC
SARs | SARs - Early Alert | Implement Early Alert system | Needs SOW & Prioritization | 3. Not Started | N/A | 4. Strategic Plan | 5. Unknown | 8. Unknown | 0% | SS RRT
Colleague | Colleague - B&N API | Barnes & Noble integration with Colleague | Need to complete SOW; Product changed, assessing new capability | 3. Not Started | 2020-08-01 | 5. Improvements | 4. Low | 6. Small | 0% | On Prior List |  | Jim Dorris
Colleague | Colleague - Ellucian Mobile | Colleague mobile application for students | Colleague mobile application for students (dependency on Colleague Financial Aid and Self Service build out) | 3. Not Started | Sum 2021 | 5. Improvements | 4. Low | 8. Unknown | 0% | TCC | Colleague - Financial Aid
Microsoft | Sharepoint | Implement Sharepoint for depts, committees, etc | On hold, may use new CMS instead | 3. Not Started | N/A | 5. Improvements | 4. Low | 1. Very Large | 0% | On Prior List | Omni Update - Website | Gabe Neri
Workday | Workday - Mobile | Workday Mobile application for employees and prospective employees | Need to discover security aspects to mobile - will look at this after VoIP | 3. Not Started | N/A | 5. Improvements | 4. Low | 6. Small | 0% | Workday SC |  | Shane Stewart | Steve Abat | Eugene Davis
Workday | Workday - P-cards | Re-engineer the procurement card process and implement in Workday | Might cancel this project | 3. Not Started | N/A | 5. Improvements | 4. Low | 8. Unknown | 0% | Workday SC |  | Shane Stewart
Workday | Workday - Purchasing "Punchouts" | Implement purchasing pre-set "punchouts" for select vendors (e.g., Dell) in Workday | Need project plan | 3. Not Started | N/A | 5. Improvements | 4. Low | 6. Small | 0% | Workday SC |  | Shane Stewart
25Live | 25Live - CollegeNet | Implement CollegeNet product from 25Live | Needs SOW & Prioritization | 3. Not Started | N/A | 5. Improvements | 5. Unknown | 8. Unknown | 0% | SS RRT
ImageNow | ImageNow - Perceptive Content | Implement upgraded cloud-based Perceptive Experience product | Needs SOW and prioritization | 3. Not Started | N/A | 5. Improvements | 5. Unknown | 2. Large | 0% | SS RRT
ImageNow | ImageNow - Web Scanning | Implement web scanning module from ImageNow | Needs SOW & Prioritization | 3. Not Started | N/A | 5. Improvements | 5. Unknown | 8. Unknown | 0% | SS RRT
? | One Card System | ID Card, Access control, student services | Needs SOW & Prioritization | 3. Not Started | N/A | 5. Improvements | 5. Unknown | 8. Unknown | 0% | SS RRT
SARs | SARs - Waitlisting | Implement SARs waitlisting module | Needs SOW & Prioritization | 3. Not Started | N/A | 5. Improvements | 5. Unknown | 8. Unknown | 0% | SS RRT
Telehealth | Telehealth System | Implement Telehealth system | Needs SOW & Prioritization | 3. Not Started | N/A | 5. Improvements | 5. Unknown | 8. Unknown | 0% | SS RRT
Colleague | Colleague - AB1313 | Remove hold restrictions on Transcripts | Programming changes has begun, investigating SDSU transcript issue | 4. Completed | 2020-02-01 | 1. Enrollment | 1. Critical | 6. Small | 100% | TAC |  | Laura Murphey | John Saric
Colleague | Colleague - Priority Reg Process | Modify data source for priority registration process | Process completed and put into production end of October | 4. Completed | 2019-10-01 | 1. Enrollment | 1. Critical | 6. Small | 100% | TAC |  | Eric Lane | Laura Murphey
Colleague | Colleague - GC ESL Assessment | Implement GC ESL assessment tool in WebAdvisor | Placement tool created; In testing with stakeholders | 4. Completed | 2020-07-31 | 1. Enrollment | 2. High | 3. Med-Large | 100% | Tech RRT |  | Brian Nath (c) | Mark Chan | Laura Murphey | Richard Beres (c)
SARs | SARs e-Advising | Upgrade SARS to allow for online counseling sessions | Need update from Colleges | 4. Completed | N/A | 1. Enrollment | 2. High | 4. Medium | 100% | SS RRT |  | Asma AbuShadi | Jessica McKean
Colleague | Colleague - AB1504 | Increase student fee to $2, send $1 to the state | Solution tested; Implementation to occur on May 8 | 4. Completed | 2020-04-26 | 2. Compliance | 1. Critical | 4. Medium | 100% | TAC |  | Mark Chan | Laura Murphey
Colleague | Colleague - COVID EW Programming Changes | Implement processing all withdrawals as EW due to COVID | Solution tested and implemented | 4. Completed | 2020-04-30 | 2. Compliance | 1. Critical | 6. Small | 100% | Operational |  | Mark Chan | Laura Murphey
Colleague | Colleague - COVID NP Programming Changes | Implement taking out NP grades from probation programming | Completed | 4. Completed | 2020-06-15 | 2. Compliance | 1. Critical | 6. Small | 100% | Operational |  | Mark Chan | Laura Murphey
Colleague | Colleague - MIS Data for CB25/CB26 | Code new course types in Colleague | Created course type fields and coding to capture these data elements; Instructional Ops inputting correct values | 4. Completed | 2019-10-01 | 2. Compliance | 1. Critical | 6. Small | 100% | TAC |  | Eric Lane | Laura Murphey
Colleague | Colleague - W/EW Refund Fix | Fix W/EW data and corresponding refunds | W/EW refund fix and report of data has been completed | 4. Completed | 2020-07-23 | 2. Compliance | 1. Critical | 2. Large | 100% | Operational |  | Brian Nath (c) | Eric Lane (c) | Jim Dorris | Laura Murphey
Colleague | Colleague - AB 19 Promise Coding | Create process for coding and processing students eligible for AB19 funds | AB 2 configuration and lingering issues being addressed | 4. Completed | 2018-09-01 | 2. Compliance | 2. High | 2. Large | 100% | Alliance SC |  | Shari Waters | Eric Lane | Laura Murphey
Colleague | Colleague - MIS Data for SB38 | Program new student race/ethnicity codes | Colleague valcodes tables built; data validated; Go-Live on May 12 | 4. Completed | 2019-11-20 | 2. Compliance | 2. High | 3. Med-Large | 100% | Operational | Colleague - CRM Recruit Phase II | Laura Murphey | Jon Saric | Eric Lane (c) | Brian Nath (c)
Colleague | Colleague - Modify DQ Programming | Adjust Programming for DQ process to remove DQ after two semesters of non-enrollment | New process put into production on 1/10 | 4. Completed | 2020-01-08 | 3. Infrastructure | 1. Critical | 6. Small | 100% | TAC |  | Eric Lane | Brian Nath | Sandy Mistretta
Colleague | Colleague - Update Self Service to v2.23 (Mar 2019) | Update Colleague Self-Service and Student Planning to current version | Project and documentation completed | 4. Completed | FA 2019 | 3. Infrastructure | 1. Critical | 2. Large | 100% | Operational |  | Jim Dorris | Eric Lane | Laura Murphey
Colleague | Colleague - Update Self Service to v2.25 (Oct 2019) | Update Colleague Self-Service and Student Planning to current version | Testing occurred; Scheduled for production on Dec 6 | 4. Completed | FA 2019 | 3. Infrastructure | 1. Critical | 2. Large | 100% | Operational |  | Jim Dorris | Eric Lane | Laura Murphey
Colleague | Colleague - Upgrade to Self Service v2.22 (Dec 2018) | Update Colleague, Self Service, and Student Planning to current version | 1098T, Colleague update complete; Self Service & Student Planning v2.22 in test | 4. Completed | 2019-01-01 | 3. Infrastructure | 1. Critical | 2. Large | 100% | Operational |  | Jim Dorris | Eric Lane | Laura Murphey
Colleague | Colleague - Create new CC Exercise Science Division | Create new CC Exercise Science Division and reconfigure department reporting structure | Reached out to Ellucian to get support on creating this change | 4. Completed | 2019-06-01 | 3. Infrastructure | 2. High | 6. Small | 100% | TAC |  | Eric Lane
ImageNow | Document Imaging Upgrade | ImageNow - upgrade file system configuration | Deployment ready; New go-live date on 5/21 | 4. Completed | 2020-01-09 | 3. Infrastructure | 2. High | 3. Med-Large | 100% | TAC |  | Brian Nath (c) | John Sorman
Ex Libris | Ex Libris (LSP) Project | Implement new library services platform from Ex Libris | Library system went live on 1/13 | 4. Completed | 2020-01-13 | 3. Infrastructure | 2. High | 1. Very Large | 100% | TCC |  | Brian Nath | Frank Moore | Richard Beres
Colleague | Colleague - Change Refund Date (Optimization) | Change the refund date to match the withdrawal date | A&R signed off on solution in Test; Ready to roll out for summer | 4. Completed | 2020-05-31 | 3. Infrastructure | 3. Medium | 5. Sm-Medium | 100% | TCC |  | Shari Waters (c) | Eric Lane (c) | Mark Chan | Laura Murphey
SARs | SARsTRAK - Tutoring | Track Lab Usage | Use SARs Trac to replace Red Canyon at GC | 4. Completed |  | 3. Infrastructure | 3. Medium | 6. Small | 100% | TAC |  | Asma AbuShadi | Jessica McKean | Jim Dorris
Workday | Workday - Foundation Finance Migration | Migrate Foundation finance from iFAS to Workday | Configuration and testing ongoing; Go-Live Date pushed to July 2020 due company naming issue | 4. Completed | 2020-07-01 | 3. Infrastructure | 3. Medium | 2. Large | 100% | Workday SC |  | Shane Stewart | Michael Carr
OpenCCCApply | Open CCCApply Authentication |  |  | 4. Completed |  | 3. Infrastructure | 4. Low |  | 100% | Operational
Red Canyon | Red Canyon Removal | Remove Red Canyon stations from Grossmont College labs |  | 4. Completed | 2019-09-01 | 3. Infrastructure | 4. Low | 6. Small | 100% | Operational |  | Brian Nath
Colleague | Colleague - Audit of Degree Audit | Audit our current degree audit processes to assess viability of switching to Colleague | Onsite audit occurring Dec 16-19, 2019 | 4. Completed | 2019-12-19 | 4. Strategic Plan | 2. High | 1. Very Large | 100% | TCC |  | Shari Waters | Eric Lane | Laura Murphey
Colleague | Colleague - CRM Recruit Phase I | Colleague outreach module for prospective students | Testing will occur in February; On target for Phase 1 Go-Live date adjusted to Apr 22 | 4. Completed | 2019-03-01 | 4. Strategic Plan | 2. High | 1. Very Large | 100% | TCC |  | Shari Waters | Eric Lane | Laura Murphey
Canvas | Canvas - Automate Faculty Email | Automate/modify import of faculty emails from Colleague to Canvas | Worked with college ICS departments and HR to automate this import | 4. Completed | 2019-08-01 | 5. Improvements | 2. High | 5. Sm-Medium | 100% | TCC |  | Shane Stewart | Frank Moore
25Live | 25Live - Linx Scheduling Upgrade | Linx interface with Colleague to feed room scheduling process | Project and documentation completed | 4. Completed | 2019-12-01 | 5. Improvements | 3. Medium | 4. Medium | 100% | Operational |  | Jim Dorris | Alla Lyukin
EvaluationKit | Course Evaluation Software | EvaluationKit pilot occurring at Grossmont College for online courses | Pilots still ongoing for Fall 2019; Decision for full implementation needs to be made for Spring 2020 | 4. Completed | 2020-01-01 | 5. Improvements | 3. Medium | 7. Very Small | 100% | TCC
Medicat | Medicat | Software to track health services at Grossmont College | Discovery for Colleague integration | 4. Completed |  | 5. Improvements | 3. Medium | 6. Small | 100% | TCC |  | Brian Nath | John Sorman
Cornerstone | Professional Development Software | Cornerstone software | IT portions of the project are complete; Config Team needs to develop communication plan | 4. Completed | 2019-12-01 | 5. Improvements | 3. Medium | 5. Sm-Medium | 100% | TCC |  | Richard Beres (c) | Brian Nath (c)

## Infrastructure List
System | Project | Description | Update | Status | Target Date | Category | Priority | Complexity | % Complete | Source | Dependency | Resource 1 | Resource 2 | Resource 3 | Resource 4
Building | Building - GC PVAC | Install and configure switches, WAPs, cabling, ports, and phones for PVAC | Project almost complete; IT will still need to take care of little projects here and there. | 1. In Progress | 2020-03-20 | 3. Infrastructure | 1. Critical | 4. Medium | 100% | Facilities MP | Building Completion | Brian Merrill © | Eugene Davis
Dell | Dell - Backup System | Install new backup servers/system | Equipment installed at GC - CC; Vendor and IT engaged in setup. | 1. In Progress | 2020-09-30 | 3. Infrastructure | 1. Critical | 2. Large | 100% | Tech Plan | Delivery/Planning/Deployment | Steve Abat | Michael Carr | Jerry Williamson
Building | Building - GC Building 36 | Install and configure switches, WAPs, cabling, ports, and phones for Building 36 | Not Started - We need to wait until the building is ready before we can do this | 1. In Progress | 2020-12-20 | 3. Infrastructure | 1. Critical | 4. Medium | 10% | Facilities MP | Meetings and Building Completion | Brian Merrill © | Steve Abat
Building | Building - CC Student Services | Plan IT infrastructure for CC Student Services Building | Meetings are ongoing | 1. In Progress | 2020-12-20 | 3. Infrastructure | 1. Critical | 4. Medium | 0% | Facilities MP | Meetings and Building Completion | Brian Merrill © | Eugene Davis
VM Ware | VM Ware Expansion | Expand VMware at Cuyamaca; PR for VMware and servers processed. | Need to expand VM environment for disaster recovery of backup tapes districtwide. | 1. In Progress | 2020-12-20 | 3. Infrastructure | 1. Critical | 6. Small | 90% | Operational | Approval/Purchasing/Delivery | Robert Mountain | Eugene Davis
Microsoft | Microsoft - Windows Virtual Desktop | Set up and pilot the MS Windows virtual desktop environment for remote access | VDs installed; Developing "golden image"; MS needs to provide new update in order to configure support options | 1. In Progress | 2020-09-30 | 3. Infrastructure | 2. High | 2. Large | 90% | Tech RRT |  | Steve Abat | Eugene Davis
VoIP | VoIP - Softphone Feature Rollout | Implement the Mitel Softphone feature for remote calling functionality | Softphones are rolling out to the campus community, starting with departments with student-facing services | 1. In Progress | 2020-07-31 | 3. Infrastructure | 2. High | 5. Sm-Medium | 50% | Tech RRT |  | Steve Abat | Jerry Williamson | Brian Merrill
Microsoft | Microsoft - Windows 10 Image | Create new Windows 10 image (Nov 2019) and implement Office 2019 | In order to stay secure and updated on Windows 10 we need to create another image based on last Novembers release; Networking team actively working on this project | 1. In Progress | 2020-08-31 | 3. Infrastructure | 2. High | 4. Medium | 100% | Operational | Resources | Steve Abat | Eugene Davis
Building | Building - Outdoor WiFi | Install WAPs in high-use outside areas (e.g., GC Quad, CC Student Center, etc.) | Project is now in process; Identifying scope, including parking lots at GC-CC; Temporary solution scheduled for installation the week of 9/14 | 1. In Progress | 2020-07-31 | 3. Infrastructure | 2. High | 5. Sm-Medium | 33% | TCC |  | Brian Merrill ©
Microsoft | Microsoft - Teams | Implement MS Teams as a collaborative tools for employees | IT is researching backend administration and support parameters with Microsoft. Team is attending virtual workshop on 5/13. | 1. In Progress | 2020-09-30 | 3. Infrastructure | 3. Medium | 5. Sm-Medium | 10% | Tech RRT |  | Steve Abat | Jerry Williamson
Palo Alto | Palo Alto - Internal Firewall | Install internal firewall and replace text-based access control list | We will modernize our internal security by getting rid of our text based access control lists and moving to a dynamic Palo Alto Firewall. | 1. In Progress | 2020-12-31 | 5. Improvements | 3. Medium | 2. Large | 20% | Security Plan | Resources | Eugene Davis | Steve Abat
Cloud Backup | Cloud Backup System | Transition from tape backups to offsite cloud backups | After our new backup setup is purchased and completed, we need to begin work on moving our tape backups to the cloud. | 3. Not Started | 2021-06-30 | 3. Infrastructure | 2. High | 2. Large | 0% | Tech Plan | Dell - Backup System | Steve Abat | Staff | Michael Carr | Jerry Williamson
UPS | UPS Installation | Install backup power for all switches districtwide | The colleges have requested that we install UPS systems in all of our MDF/IDF closets that support phones--need to document all closets. | 3. Not Started | 2021-06-30 | 3. Infrastructure | 3. Medium | 1. Very Large | 0% | Tech Plan | Resources | Brian Merrill | Steve Abat
Workspace One | Workspace One - Mobile Device Management | GC ICS has requested this software to manage mobile devices | We are now investigating Microsoft Endpoint Management for remote devices. | 3. Not Started | 2020-08-31 | 5. Improvements | 3. Medium | 6. Small | 0% | Tech RRT | Resources | Steve Abat | Robert Mountain
Active Directory | Active Directory Cleanup | Clean up active directory of all unused accounts and create process for employee terminations/position changes | This is a security risk after years of neglect. | 3. Not Started | 2020-12-20 | 5. Improvements | 3. Medium | 4. Medium | 0% | Operational | Resources | Steve Abat | Eugene Davis
Building | Building - GCCCD Server Room | Upgrade HVAC in server room and remodel IT Work Room | This project is currently being worked on and should be completed by July 2020? Gafcon in charge of project | 4. Completed | 2020-04-20 | 3. Infrastructure | 1. Critical | 6. Small | 100% | Facilities MP | AC Installation | Brian Merrill © | Steve Abat | Jerry Williamson
Microsoft | Microsoft - Windows 7 Extended License | Deploy Windows 7 and Server 2008 R2 extended support licenses for security | Windows 7 and Server 2008 R2 are both EOL, we need to deploy this licensing to stay current on Windows 7 and Server 2008 R2 security. | 4. Completed | 2020-02-13 | 3. Infrastructure | 1. Critical | 6. Small | 100% | Operational | Resources | Steve Abat | Eugene Davis
Building | Building - GC Trailer Expansion (Lot 1) | Install and configure switches, WAPs, cabling, ports, and phones for new trailers in Lot 1 | In Progress | 4. Completed | 2020-03-20 | 3. Infrastructure | 1. Critical | 5. Sm-Medium | 100% | Facilities MP | Communication with Gafcon | Brian Merrill © | Eugene Davis
Building | Building - GC Trailer Expansion (Lot 5) | Install and configure switches, WAPs, cabling, ports, and phones for new trailers in Lot 5 | Done | 4. Completed | N/A | 3. Infrastructure | 1. Critical | 5. Sm-Medium | 100% | Facilities MP | N/A | Brian Merrill © | Eugene Davis
Building | Building - GC Hyde Gallery Temp Space | Install and configure network setup for Hyde Gallery temporary space | Done | 4. Completed | 2020-02-20 | 3. Infrastructure | 1. Critical | 5. Sm-Medium | 100% | Facilities MP | N/A | N/A | N/A
Building | Building - GC Building 31 | Install and configure switches, WAPs, cabling, ports, and phones for Building 31 | Done | 4. Completed | 2020-02-20 | 3. Infrastructure | 1. Critical | 5. Sm-Medium | 100% | Facilities MP | Building Completion | Brian Merrill © | Eugene Davis
Microsoft | Microsoft - Office 365 Licensing | Develop a standard procedure for issuing O365 licensing and reallocate existing licenses. | The licensing model in office 365 is in disarray due to a shift in Microsoft licensing and Pricing. We will need to manage licenses for SSO and password resets. | 4. Completed | 2020-07-20 | 3. Infrastructure | 2. High | 2. Large | 100% | Operational | Review in July Time Fram | Steve Abat | Jerry Williamson
Microsoft | Microsoft - OneDrive | Develop support parameters and documentation for OneDrive rollout | Creating documentation and website links; Developing rollout communication; Rolled out on 6/4. | 4. Completed | 2020-05-29 | 3. Infrastructure | 2. High | 6. Small | 100% | Tech RRT |  | Jerry Williamson
Microsoft | Microsoft - Certificate Renewal | Renew MS Office 365 and Exchange certificates by Mar 2020 | This is the issue we had a couple years ago where we lost access to email because of certificates expiring. We need to create new certificates in March of 2020, this is a reminder more than anything. | 4. Completed | 2020-02-28 | 3. Infrastructure | 2. High | 6. Small | 100% | Operational | Awareness | Eugene Davis | Steve Abat
Microsoft | Microsoft - Certificate Management | Engage with MS consultants to create plan to manage MS certificates | We are meeting with Microsoft this week Tuesday, Wednesday and Thursday to get a handle on our internnal Microsoft Certificates. | 4. Completed | 2020-02-20 | 3. Infrastructure | 2. High | 5. Sm-Medium | 100% | Operational | Training | Eugene Davis | Steve Abat
VoIP | VoIP - Switch Upgrades | Need to purchase and install new VoIP switches to handle PRI | Procurement begun for new switches; Switches will be received and deployed on 4/6 | 4. Completed | 2020-02-20 | 3. Infrastructure | 3. Medium | 6. Small | 100% | Tech Plan | Purchasing / Delivery | Brian Merrill | Steve Abat
Microsoft | Microsoft - Student Tenant | Transfer control of student tenant to ICS | O365 "viral" student tenant has been migrated over to GCCCD | 4. Completed | 2020-07-31 | 3. Infrastructure | 4. Low | 7. Very Small | 100% | Tech RRT |  | Steve Abat | Jerry Williamson

## Codes
1. In Progress | 1. Very Large | 1. Enrollment | 1. Critical
2. On Hold | 2. Large | 2. Compliance | 2. High
3. Not Started | 3. Med-Large | 3. Infrastructure | 3. Medium
4. Completed | 4. Medium | 4. Strategic Plan | 4. Low
5. Canceled | 5. Sm-Medium | 5. Improvements | 5. Unknown
6. Small
7. Very Small
8. Unknown