## Tasks
Issue | Resolved? | Client Notes | Beacon notes | Source | Requested | Answered | Reference | order
The background for the smaller rotator on the lower portion of the home page should be a gray gradient with the active picture having a blue dot, not the greenish solid color and gray dot that seems to come from the district site. Please look at the current CC home page on Cascade Server. | Yes |  |  | Rhonda | 2013-09-20 | 2014-12-11 | email from Kerry on 12/11/14 | 1
On the main navbar, it should say “About Us” instead of “About” to match the district site. | Yes |  |  | Rhonda | 2013-09-20 | 2014-12-11 | email from Kerry on 12/11/14 | 2
Links in the footer should go to the pages already linked in the current Cuyamaca home page on Cascade Server | Later | Annette said this is done in sample site, but it isn't |  | Rhonda | 2013-09-20 | 2014-12-11 | email from Kerry on 12/11/14 | 3
“A Member of the Grossmont-Cuyamaca Community College District” should be in one line | Yes |  |  | Rhonda | 2013-09-20 | 2014-12-11 | email from Kerry on 12/11/14 | 4
The address in the footer should be a link to Maps & Directions | Yes |  |  | Rhonda | 2013-09-20 | 2014-12-11 | email from Kerry on 12/11/14 | 5
I don’t see a need for a copyright statement. There isn’t one on the District site. | Yes | with expansion of footer, this is no longer a waste of space |  | Rhonda | 2013-09-20 | 2014-12-11 | email from Kerry on 12/11/14 | 6
The breadcrumbs don’t lead back to the home page | Yes |  |  | Rhonda | 2013-09-20 | 2014-12-11 | email from Kerry on 12/11/14 | 9
The breadcrumbs bar should be slightly darker than the navigation bar and the navigation bar seems too light. | Yes |  |  | Rhonda | 2013-09-20 | 2014-12-11 | email from Kerry on 12/11/14 | 10
The picture in buckets should be a link as well as the text | Yes | Agree-- I have requested that this changes be made in the sample site |  | Rhonda | 2013-09-20 | 2014-12-11 | email from Kerry on 12/11/14 | 11
The » characters are distracting | Yes | These can be removed or modified if desired/approved. |  | Rhonda | 2013-09-20 | 2014-12-11 | email from Kerry on 12/11/14 | 12
Class Descriptions and Certificate and Degree information for academic department websites. | Yes | See http://cuyamaca.beacontest.com/programs-departments/graphic-design/class-descriptions.html links will have to go to a pdf |  | Rhonda | 2013-09-20 | 2014-12-11 | email from Kerry on 12/11/14 | 13
Will content owners be able to manipulate widgets? | Yes | Anyone with the CMS permissions to create widgets can edit them. However, if the widget is shared on multiple pages, they will need to be aware that changing a widget will change the display on all connected pages. If sharing widgets doesn’t work for your environment/editors, then we can simply add these as tools that can be used on each page in the right column, but not shared. That is the kind of feedback that we need before the final deliverables are produced. |  | WATF | 2013-12-11 |  | http://www.cuyamaca.edu/in/committees/watf/files/minutes/2013-12-11-WATF-minutes.pdf - answers in http://www.cuyamaca.edu/in/committees/watf/files/agendas/2014-01-15-watf-agenda.pdf | 14
Are the college task forces to pre-determine (provide input on) what the buckets are? | Yes | during the content phase |  | WATF | 2013-12-12 |  | http://www.cuyamaca.edu/in/committees/watf/files/minutes/2013-12-11-WATF-minutes.pdf - answers in http://www.cuyamaca.edu/in/committees/watf/files/agendas/2014-01-15-watf-agenda.pdf | 15
What are the technical specs for the photos on the home page? | Yes | 1158 x 563 pixels w sides faded to white |  | WATF | 2013-12-13 |  | http://www.cuyamaca.edu/in/committees/watf/files/minutes/2013-12-11-WATF-minutes.pdf - answers in http://www.cuyamaca.edu/in/committees/watf/files/agendas/2014-01-15-watf-agenda.pdf | 16
Should we have established guidelines for the home page images? | Later | Should we have a policy that no text is added to these images because when reduced to phone size, they won't display properly? Photos should be tied in with upcoming events and college programs – show a graduation photo at commencement time; photos of departments such as ornamental horticulture and auto tech. Photos should be changed throughout the year. |  | WATF | 2013-12-14 |  | http://www.cuyamaca.edu/in/committees/watf/files/minutes/2013-12-11-WATF-minutes.pdf - answers in http://www.cuyamaca.edu/in/committees/watf/files/agendas/2014-01-15-watf-agenda.pdf | 17
2.1.2.1 can we add items to the “Find” menu in the header, such as campus officehours, which is a printable, pdf document | Yes |  |  | WATF | 2014-01-14 |  | http://www.cuyamaca.edu/in/committees/watf/files/minutes/2014-01-14-WATF-minutes.pdf | 18
2.1.2.1 Is there a way we can print/share for the home page like we do on the interior pages? | Yes | The original designs don’t really have a place that would easily accommodate these icons without looking “cluttered” |  | WATF | 2014-01-14 | 2014-01-28 | http://www.cuyamaca.edu/in/committees/watf/files/minutes/2014-01-14-WATF-minutes.pdf | 19
2.1.2.2 Change "About" to "About Us" and put it and Campus Life on 2 lines for consistency | Yes |  |  | WATF | 2014-01-14 | 2014-01-28 | http://www.cuyamaca.edu/in/committees/watf/files/minutes/2014-01-14-WATF-minutes.pdf | 20
2.1.2.2.1 Task Force recommends a large horizontal menu | Yes | on wireframe v3 |  | WATF | 2014-01-14 | 2014-01-28 | http://www.cuyamaca.edu/in/committees/watf/files/minutes/2014-01-14-WATF-minutes.pdf | 21
2.1.2.2.1 Determine number of Call to Action buttons allowed on mega menu | Yes | There will be a maximum of one image and one call to action button per drop down menu. The image and call-to-action buttons will always be displayed in the last/right column of the menu. If desired, only an image or only a call-to-action button can be displayed on any menu |  | WATF | 2014-01-14 |  | http://www.cuyamaca.edu/in/committees/watf/files/minutes/2014-01-14-WATF-minutes.pdf | 22
2.1.2.2.1 Would site have to be re-published if navigation menu is changed? | Yes | answer is no, this will be an include file for footer and navigation. See http://intranet.gcccd.edu/website-steering/documents/GCCC-Meeting-agenda-1-28-14.pdf |  | WATF | 2014-01-14 | 2014-01-28 | http://www.cuyamaca.edu/in/committees/watf/files/minutes/2014-01-14-WATF-minutes.pdf | 23
2.1.2.3 Will the left navigation menu follow viewer as they scroll on long vertical pages? | Yes | We don’t normally have the left navigation scroll down with the user due to the additional code and page load time that it requires (particularly for a responsive site). |  | WATF | 2014-01-14 | 2014-01-28 | http://www.cuyamaca.edu/in/committees/watf/files/minutes/2014-01-14-WATF-minutes.pdf | 24
2.1.2.3 Use new "To Top" link from http://bit.ly/ccnewfac rather than static one at the bottom of the page | No | they implemented a solution on 1/28 that puts a static link at the bottom of the page. We need the link to move with the scroll. | Added to section 2.1.2.4 of the requirements | WATF | 2014-01-14 |  | http://www.cuyamaca.edu/in/committees/watf/files/minutes/2014-01-14-WATF-minutes.pdf | 25
2.1.2.3 Should contact info should be on right side as a widget instead of on left navigation? On mobile, where would contact info show up?? | Yes | We don’t recommend having the contact information on the right side because a right column is optional on all pages. You don’t want to train the visitor where to find that information and then have it disappear on some pages |  | WATF | 2014-01-14 | 2014-01-28 | http://www.cuyamaca.edu/in/committees/watf/files/minutes/2014-01-14-WATF-minutes.pdf | 26
2.1.2.3 Can Admissions office hours be some kind of include file that would be on all Admissions pages in the right column? | Yes | we can create a setting in Cascade that would allow any widget created on a section default page to be automatically displayed on all the children in that section. Could be applied to call to action buttons and contact information in the left column or widgets in the right column. |  | WATF | 2014-01-14 | 2014-01-28 | http://www.cuyamaca.edu/in/committees/watf/files/minutes/2014-01-14-WATF-minutes.pdf | 27
2.1.2.4 The logo on the footer should link to the home page | No | response on 1/28/14 said this was updated on the sample sites, but it isn't done yet - see http://intranet.gcccd.edu/website-steering/documents/GCCC-Meeting-agenda-1-28-14.pdf | Added to requirements in section 2.1.2.5 and to be implemented in Development phase | WATF | 2014-01-14 | 2014-01-28 | http://www.cuyamaca.edu/in/committees/watf/files/minutes/2014-01-14-WATF-minutes.pdf | 28
2.1.2.4 Can we change the icon for WebAdvisor? | Yes | on wireframe v3 |  | WATF | 2014-01-14 |  | http://www.cuyamaca.edu/in/committees/watf/files/minutes/2014-01-14-WATF-minutes.pdf | 29
2.2 We want a checkbox option within the main template to make it 2 or 3 columns and the choice to include or not include a banner. | No | Currently in Cascade, the user selects from either a 2 column or 3 column landing page, when creating the page. However, we could change this so that it is instead a “Yes/No” radio button selection like this:(see doc) | Added to requirements for Standard page template in section 2.2.1 and implemented in Development phase | WATF | 2014-01-14 | 2014-01-28 | http://www.cuyamaca.edu/in/committees/watf/files/minutes/2014-01-14-WATF-minutes.pdf | 30
2.2 The section name is forced by CSS to be uppercase. Can it be small caps instead? | Yes | Changed to upper/lower case |  | WATF | 2014-01-14 |  | http://www.cuyamaca.edu/in/committees/watf/files/minutes/2014-01-14-WATF-minutes.pdf | 31
2.2 Does breadcrumbs navigation have fixed height or does it expand if breadcrumbs are long? Is there a limit on how long breadcrumbs can be? | Yes | it expands |  | WATF | 2014-01-14 | 2014-01-28 | http://www.cuyamaca.edu/in/committees/watf/files/minutes/2014-01-14-WATF-minutes.pdf | 32
2.2.1.1 - Breadcrumb navigation may need top-level to be small caps instead of Uppercase so that some acronyms display properly. Such as CalWorks. | Yes | changed in wireframe v3 |  | Rhonda | 2014-01-14 | 2014-01-28 |  | 33
2.2.1.2 Can we change the look of the print logo so it stands out better amongst the share buttons? | Yes | changed icon |  | WATF | 2014-01-14 | 2014-01-28 | http://www.cuyamaca.edu/in/committees/watf/files/minutes/2014-01-14-WATF-minutes.pdf | 34
2.2.3.1 will there be a way to display faculty by department? | Yes | included in wireframes v3 |  | Rhonda | 2014-01-14 | 2014-01-28 | http://www.cuyamaca.edu/in/committees/watf/files/documents/Rhondas-comments-GCCCD-Business-Requirements-v1.pdf | 35
2.2.3.2 We want the faculty page set up with design and data definitions as seen on http://bit.ly/ccnewfac | No |  | To be included in Faculty addendum documentation. | Rhonda | 2014-01-14 |  | http://www.cuyamaca.edu/rhonda.bauerlein/faculty/john.smith/default2.htm | 36
2.2.3.2 We want the accordion widget to use the appearance of http://bit.ly/ccnewfac | No |  | Updated in wireframes. Both Grossmont and Cuyamaca accordions will have the same design. | Rhonda | 2014-01-14 |  | http://www.cuyamaca.edu/rhonda.bauerlein/faculty/john.smith/default2.htm | 37
2.2.3.2 We want each faculty member to have their own folder for storing their files in Cascade. The home page of that folder would be the faculty page as seen on http://bit.ly/ccnewfac | No |  | Document directory template included in requirements in section 2.2.6 | Rhonda | 2014-01-14 |  | http://www.cuyamaca.edu/in/committees/watf/files/documents/Rhondas-comments-GCCCD-Business-Requirements-v1.pdf | 38
2.2.6 Photo Galleries - The current photo galleries script uses the Prototype / Scriptaculous framework which adds unnecessary load time to the page. Prototype is barely being maintained and may be obsolete soon. Would prefer a jQuery script be used. | Yes | mockup on wireframes 3 |  | Rhonda | 2014-01-14 | 2014-01-28 | http://www.cuyamaca.edu/in/committees/watf/files/documents/Rhondas-comments-GCCCD-Business-Requirements-v1.pdf | 39
2.3.1 News - Will colleges have control over what appears here, or only the District? | Yes | This is a business decision. If Cascade users at the college are given access to the District News folder, then they will be able to add/remove/update stories. |  | Rhonda | 2014-01-14 |  | http://www.cuyamaca.edu/in/committees/watf/files/documents/Rhondas-comments-GCCCD-Business-Requirements-v1.pdf | 40
2.5 Training - can this be via webinar that is recorded and we get rights to recording? | Yes | Agreed. The training session will be recorded and posted for Grossmont/Cuyamaca to download. This has been added to the requirements document. |  | Rhonda | 2014-01-14 |  | http://www.cuyamaca.edu/in/committees/watf/files/documents/Rhondas-comments-GCCCD-Business-Requirements-v1.pdf | 41
3 Optional - Victor Devore needs to send Beacon the JavaScript and other files needed for http://www.cuyamaca.edu/admissions/deadlines.asp to see if it can be created using just a WYSIWYG in Cascade. SEE "Script" tab | No | JavaScript copied into the WYSIWYG editor usually works within Cascade, but if you could provide some sample code, we can paste into the sample sites to verify. | To be added to sample site for review | Rhonda | 2014-01-14 | 2014-01-28 | http://www.cuyamaca.edu/in/committees/watf/files/documents/Rhondas-comments-GCCCD-Business-Requirements-v1.pdf | 42
4. Client action items -Beacon recommend we use ASPX pages. We need a decision from Brian Nath about this. | No | ASPX is our strongest recommendation and is the format that we almost always use with Cascade currently. PHP, ASP and HTML are options as well—we just need a final decision. | Updated in requirements document. | Rhonda | 2014-01-14 |  | http://www.cuyamaca.edu/in/committees/watf/files/documents/Rhondas-comments-GCCCD-Business-Requirements-v1.pdf | 43
5.1 Coding languages - HTML 5 should be used whenever possible. | Yes | Agreed and added to the requirements document |  | Rhonda | 2014-01-14 | 2014-01-28 | http://www.cuyamaca.edu/in/committees/watf/files/documents/Rhondas-comments-GCCCD-Business-Requirements-v1.pdf | 44
5.1 Coding languages - jQuery 1.11 should be used, preferably via a CDN with local backup, see how Bootstrap does this at http://css-tricks.com/snippets/jquery/fallback-for-cdn-hosted-jquery/ | No |  | Beacon cannot guarantee the version of jQuery to be used, because it is highly dependent upon the functionality requirements of the website. CDN with local backup will be implemented if feasible. | Rhonda | 2014-01-23 |  | http://css-tricks.com/snippets/jquery/fallback-for-cdn-hosted-jquery/ | 45
5.2 We need more obvious active/focus states for accessibility | No | asked on 1/28 if we wanted this, yes we do. see http://intranet.gcccd.edu/website-steering/documents/GCCC-Meeting-agenda-1-28-14.pdf | Updated in requirements document. | Rhonda | 2014-01-14 |  | http://www.cuyamaca.edu/in/committees/watf/files/documents/Rhondas-comments-GCCCD-Business-Requirements-v1.pdf | 46
Department websites - no template | Yes |  |  | Rhonda | 2014-01-14 | 2014-01-28 | http://www.cuyamaca.edu/in/committees/watf/files/documents/Rhondas-comments-GCCCD-Business-Requirements-v1.pdf | 47
5.4 Smartphones - Apple iPhone 5S is current | Yes | Updated in requirements document |  | Rhonda | 2014-01-14 | 2014-01-28 | http://www.cuyamaca.edu/in/committees/watf/files/documents/Rhondas-comments-GCCCD-Business-Requirements-v1.pdf | 48
5.4 Smartphones - Samsung Galaxy S4 current version is Android 4.3 | Yes | Updated in requirements document |  | Rhonda | 2014-01-14 | 2014-01-28 | http://www.cuyamaca.edu/in/committees/watf/files/documents/Rhondas-comments-GCCCD-Business-Requirements-v1.pdf | 49
Get rid of the warning pop-up message that displays when an external link is clicked | No |  | Removed from sample sites. | Rhonda | 2014-02-23 |  |  | 50
Get rid of the icon added next to external links | No |  | Removed from sample sites. | Rhonda | 2014-02-23 |  |  | 51
Minimize page weight - compress JavaScript, do not include scripts that are not used, use sprites, etc. to reduce loading time, see https://developer.mozilla.org/en-US/docs/Web/Guide/HTML/Tips_for_authoring_fast-loading_HTML_pages | No | see Reference column for resource for doing this | Beacon will make every effort to maximize the page load time of the site once development is completed. However, this effort must be balanced with successful implementation of the functionality described in the requirements document. If the page load time is still a concern during the testing phase of the project, this can be discussed further. | Academic Senate | 2014-02-23 |  | https://developer.mozilla.org/en-US/docs/Web/Guide/HTML/Tips_for_authoring_fast-loading_HTML_pages | 52
Title metatags should not be used for breadcrumbs or navigation - title tags are needed for important SEO information that isn't appropriate for breadcrumbs | No |  | Added to requirements in section 2.2.1.1 based on email from Rhonda on 3/5 | Rhonda | 2014-02-23 |  |  | 53
Change typography to styles on http://bit.ly/cctyponew | No |  | Updated in wireframes. | Rhonda | 2014-02-23 |  |  | 54
Events and news on home page - can they scroll when the mouse hovers over the area? See vertical scroller at http://manos.malihu.gr/tuts/jquery_thumbnail_scroller.html for example | No |  | Added to requirements in section 2.3.1 | WATF | 2014-02-04 |  |  | 55
Put a link in the footer of every page that when clicked, would take you to login to the CMS editor, then directly to the page you want to edit. Use the © copyright symbol in the footer for the link, with no hover effects. | No |  | This was not included in the scope of this contract. It can be quoted separately and added to phase 1 if required. | Steering | 2014-02-25 |  |  | 56
Make social media icons in the footer smaller and put under Contact Us | No |  | Updated in wireframes. | Steering | 2014-02-25 |  |  | 57
Use Hannon Hill Calendar | No |  | Added to requirements in section 2.3.2 |  | 2014-02-25 |  |  | 58
Calendar - include option for departments to post only on department page and not on district or college calendar | No |  | Added to requirements in section 2.3.2 |  | 2014-02-25 |  |  | 59
Make sure accordion can be navigated using the keyboard | No |  | Added to requirements in section 5.2 |  | 2014-02-25 |  |  | 60
Calendar - make sure we can toggle between monthly, week, day, and agenda views | No |  | Added to requirements in section 2.3.2 |  | 2014-02-25 |  |  | 61
Calendar - iCal download doesn't work correctly in Google or Outlook on uvi example site. Need to easily add events to mobile devices | No |  | Confirmed |  | 2014-02-25 |  |  | 62
Need ability to add date last updated to bottom of inner pages. | No |  | Added to requirements in section 2.1.2.4 |  | 2014-02-25 |  |  | 63

## Script
CSS: http://www.cuyamaca.edu/admissions/css/advancedtable.css
Code:
<script src="js/advancedtable.js" type="text/javascript" language="javascript"></script>
<script language="javascript" type="text/javascript">
$().ready(function() {
$("#table2").advancedtable({loadElement: "#loader2", searchField: "#search2", searchCaseSensitive: false, ascImage: "images/up.png", descImage: "images/down.png", csv: "2014SP_DEADLINES.csv"});
});
</script>
Table is below
<h1>Academic Deadlines - Spring 2014</h1>
<h4 class="h4-fullwidth blueBckgnd">Search for your section here:</h4>
<input type="text" name="search" id="search2">
You can search by section number, your first or last name, or course number.
<h4 class="h4-fullwidth blueBckgnd">Academic Deadline Dates</h4>
<table width="100%" id="table2" class="advancedtable" border="0" cellspacing="0" cellpadding="1">
<thead>
<tr>
<th>Section</th>
<th>Course</th>
<th>Instructor</th>
<th>Start Date</th>
<th>End Date</th>
<th>Add Deadline</th>
<th>Refund (No &#39;W&#39;) Deadline</th>
<th>P/NP Deadline</th>
<th>Drop Deadline</th>
<th>Census Date</th>
</tr>
</thead>
<tbody style="text-align: center">
<tr>
<td colspan="3">Loading... Please Be Patient</td>
</tr>
</table>
<div id="loader2" style="display: none;">
<img src="images/loader.gif" alt="Loader">
</div>
</div>
I also use JQuery’s built in UI tab feature (allows students to select from spring and intersession.)
Victor DeVore
Supervisor, Admissions and Records
Cuyamaca College
E: victor.devore@gcccd.edu
P: 619-660-4030
F: 619-660-4575