## Timeline - August launch
Week ending (Sat.)
ID | Task_Name | time axis 2013-11-09 to 2015-01-10
1 | Project Management Tasks
1.01 |  | Update Project Plan | x | x | x | N/A | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x
1.02 |  | Weekly Internal Beacon Project Meeting | x | x | x | N/A | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x
1.03 |  | Client Project Meeting | 2013-11-05 | 2013-11-12 | 2013-11-19 | N/A | 2013-12-03 | 2013-12-10 | N/A | N/A | N/A | N/A | 2013-01-14 | TBD | 2013-01-28 | 2013-02-04 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD
1.04 |  | Cuyamaca committee mtg | 2013-12-14: 2013-12-11; 2014-01-25: TBD
1.05 |  | Grossmont committee mtg | 2013-12-21: 2013-12-16; 2014-01-25: TBD
2 | Analysis and Project Approval Phase
2.01 |  | Project Kick-off Meeting | 2013-11-09: 2013-11-05
2.02 |  | Preliminary deliverables provided | 2013-12-14: 2013-12-13
2.03 |  | Client feedback on all discussion topics and preliminary deliverables | 2014-03-01: 2014-02-28
2.04 |  | Final deliverables provided | 2014-03-08: 2014-03-07
2.05 |  | Analysis Phase Signoff/Approval from Client | 2014-03-15: x; 2014-03-22: 2014-03-21
3 | Information Architecture Revew Phase
3.01 |  | Client review and completion of content inventory/information architecture | bar: 2014-03-29 to 2014-05-17
3.02 |  | Final content inventory for both sites due from stakeholders | 2014-05-17: 2014-05-16
3 | Cascade Development Phase
3.01 |  | Template development | bar: 2014-03-29 to 2014-04-26
3.02 |  | Features development | bar: 2014-03-29 to 2014-04-26
3.03 |  | Cascade functionality | bar: 2014-03-29 to 2014-04-26
4 | Testing Phase
4.01 |  | Develop System Test Plan | bar: 2014-04-26
4.02 |  | Test Environment Setup | bar: 2014-04-26
4.03 |  | Perform System Testing | bar: 2014-04-26 to 2014-05-03
4.04 |  | System Testing Complete (Severity Level 1 & 2 CRs resolved) | 2014-05-03: 2014-05-02
4.05 |  | UAT Performed by Client | bar: 2014-05-10 to 2014-05-24
4.06 |  | Log Failure and Enhancement Change Requests (by Client) | 2014-05-24: 2014-05-23
4.07 |  | All Severity Level 1 & 2 Change Requests resolved | 2014-05-31: x; 2014-06-07: 2014-06-06
5 | Content Import and Integration Phase
5.01 |  | Current site download/snapshot-- Content edited on live sites after this date needs to be documented and then updated by the client on the Cascade site after CMS training. | 2014-06-14: TBD
5.02 |  | Content import-- pages from old sites imported and saved in old site structure within Cascade (included in current budget) | bar: 2014-06-14 to 2014-06-28
5.03 |  | Content Integration-- Move imported pages of old site into new navigational schema and select site template (not included in current budget) | bar: 2014-06-28 to 2014-08-16
5.04 |  | Cascade user training | 2014-06-28: TBD; 2014-08-16: TBD
5.05 |  | College content owners review and edit content as needed | bar: 2014-08-23 to 2014-09-13
6 | Final Site Testing and Launch
6.01 |  | Final site testing (client and Beacon) | bar: 2014-09-20 to 2014-09-27
6.02 |  | Client approval for launch | 2014-09-27: TBD
6.03 |  | "Go Live" Date | 2014-10-04: TBD
6.04 |  | Production Release Verification | 2014-10-04: TBD
6.05 |  | Implementation Phase Signoff/Approval from Client | 2014-10-04: TBD
Key
Completed
Client tasks
Note on N6: Fowler, Annette: Prelim deliverables
Note on O6: Fowler, Annette: Flex week workshop
Note on P6: Fowler, Annette: Discuss final deliverables

## Client Action Items
# | Task | Responsible | Due | Status | Comments
1 | Formal project communication plan | Anne/Shari/Kerry | 11/19 (progress report) | Complete | Include location of public project documentation and option for feedback
2 | Determine members of college committee | All | 11/19 (progress report) | Complete
3 | Flex week workshop organization | Sue for Grossmont, Kerry for Cuyamaca, Anne will be a point person | 2014-01-25 | Complete
4 | Provide August registration dates for each college to determine final launch date(s) | Jeff for Grossmont, Kerry for Cuyamaca | 2013-12-10 | Complete | Provided on 12/10 by Debbie: Summer 2014 ends Jul 31 Fall 2014 Registration: Jul 14 – Aug 15 Fall Semester starts Aug 18 (Professional Development Week for faculty is the week before)
5 | Provide Grossmont graphical standards, if available, as reference for selection of 8-12 “standard” color options for bucket background colors | ? | 2013-12-03 | Complete | Check with Jamie
6 | Arrange for meeting room for task force meetings | Debbie | 2013-11-12 | Complete
7 | Determine administrator priveldges for each college: • Can determine folders and pages that can be edited and/or viewed, what toolbar options can be seen in the editor, what types of documents/files can be uploaded, etc. • Administrators—District, Grossmont, Cuyamaca, All? • Types of User groups—page editors, page approvers, administrators, etc. • Needs to be documented by client before CMS client training | IT | Before content integration begins (May 2014)
8 | Determine format of pages (HTML/PHP/ASP/ASPX): • Current district site is HTML and Cuyamaca and Grossmont are ASP | IT | Before final development begins (Feb 2014)
9 | Determine bucket design (background color vs. icons) | Committee
10 | Approve mega menu design | Committee
11 | Approve footer design update | Committee

## Questions for College Committee
# | Section/Area | Question | Date Noted
1 | Faculty template | Would faculty members like to have the option to create an unlimited number of sub-pages in Cascade within their faculty profile? Would require Cascade user ids and training for those that would like to create those pages. | 2013-11-12
2 | Faculty template | Are there other sub-pages besides “Introduction” that should be included (and maintained) for every faculty member (i.e. “Resources”)? Note: links to external websites (like Blackboard or personal websites) could be included in left navigation for each faculty member, as needed. | 2013-11-12
3 | Faculty template | Should administration and/or staff members also have profile pages? | 2013-11-12
4 | Faculty template | Should the option for accordions and buckets be provided on faculty pages? | 2013-11-12
5 | Cascade | Should all content editors be able to create landing pages, or only standard two and three column pages? | 2013-11-12

## Beacon Action Items
# | Section/Page | Task | Status | Comments
16 | Calendar | Contact collegenet re: calendaring options | Complete | Feedback to be provided with final deliverables
17 | Calendar | Provide list of pros/cons between Google, Hannon Hill and R25 calendars | In progress
4 | Footer | Research: Can additional social media icons can be added by CMS admin and please confirm that accounts can be edited/updated by CMS admin | Complete | Confirmed, additional social media icons can be added by Admins. Which administrators should be added to allow editing these items?
5 | Header | Change "Find People" label to "Find:" in header drop down. Add "Security" and "Accreditation" as drop down options. Confirm that a Cascade admin could add/remove other links. | Complete
14 | Interior | Research: Would like to be able to use accordions and buckets on three column standard and landing pages. | Complete | See http://grossmont.beacontest.com/landing-3-col.html
15 | Interior | Research: Can we add ability to pick background color of buckets from set of 8-12 colors (TBD) | Complete | Not recommended by our designer. See "Screenshots" tab for how this might be displayed. Our designer notes that the different colors don't
18 | Interior | Add social media sharing icons to interior templates | In progress
1 | Design | Provide dimensions for home page banners and bucket thumbnail images so that image creation can be started by each college as soon as possible | Complete | 1158 x 563 – homepage slider 293 x 215 – homepage featurette 241 x 161 – Interior bucket spots
2 | Faculty template | Build faculty listing, faculty detail and department landing pages in microsites | Complete | http://cuyamaca.beacontest.com/faculty-staff/default.html http://grossmont.beacontest.com/faculty-staff/default.html
3 | Footer | Make footer a tad taller so that more links can be accommodated in the 3rd and 4th column. (add "Safety") | Complete | To be included in designs provided with preliminary deliverables
7 | Home page - Banner | Add ability "Read more" link in caption text to file, internal or external page. Each banner can have a different, but optional, link. Current "Apply" button functionality does not change. | Complete | In test - http://gcccd.beacontest.com, http://cuyamaca.beacontest.com, http://grossmont.beacontest.com/. Note, banner image link not recommended.
8 | Home page - Banner | Full width slider - slider caption will have a Read More link (optional) | Complete
11 | Home page - Featured Image | Looks like the number of featured images is unlimited in Cascade? Suggest limiting to 8 or so? | Complete | Recommend limiting to 8 slides
9 | Home page - Featured Image | Design controls for navigation between slides | Complete | To be included in designs provided with preliminary deliverables
10 | Home page - Featured Image | Ability to link image to file, internal or external page | Complete | In test - http://gcccd.beacontest.com, http://cuyamaca.beacontest.com, http://grossmont.beacontest.com/
12 | Home page - Featured Image | Auto rotate images | Complete | In test - http://gcccd.beacontest.com, http://cuyamaca.beacontest.com, http://grossmont.beacontest.com/
13 | Interior | Design a system of 8-12 background colors for the buckets based on the color palates currently being used. | Complete | To be included in designs provided with preliminary deliverables
6 | Top Navigation | Top navigation-- Dropdown menus - 2 versions - one with tier 3 and one with tier 3&4 (mega dropdown) | Complete | To be included in designs provided with preliminary deliverables
19 | http://cuyamaca.beacontest.com/future-students/default.html | The address in the footer should be a link to Maps & Directions | In progress
20 | http://cuyamaca.beacontest.com/current-students/technology-resources.html | Breadcrumbs should link back to home page | Complete
21 | /programs-departments/default.html | 3. This content totally out of place. They copied in one of the DSPS pages here, which should be linking to the whole DSPS site: http://www.cuyamaca.edu/dsps/ 4. DSPS High Tech Center should be an h3 and not smaller than the h2. Headers should be progressively smaller, the higher the number. | In progress
22 | /programs-departments/default.html | Link image as well as headline text | In progress
23 | Interior | Links in the footer should go to the pages already linked in the current Cuyamaca home page on Cascade Server. | In progress
24 | Accordian | Create sample page with this functionlaity: http://www.cuyamaca.edu/gd/class-desc.asp | In progress
25 | Header | Add show all button above accordian to open all items | Complete
26 | Header | Make sure logo has alt text and that it contains the full college name | In progress
27 | Header | Client thinks the blue being used on mini site doesn't match original design here: http://cmsc.gcccd.edu/admissions/sub-page.html and wants to know if black line can be added back in. | Complete
28 | Home | Make background for the featured area a gray gradient like the News and Events sections | In progress

## References
Items | URL | Comment
Intranet site | http://intranet.gcccd.edu/website-steering/default.html
Grossmont sample site | http://grossmont.beacontest.com/default.html
Cuyamaca sample site | http://cuyamaca.beacontest.com/default.html
Original Cuyamaca designs | http://cmsc.gcccd.edu
Original Grossmont designs | http://cmsg.gcccd.edu
FTP location for meeting recordings | Host: ftp.beacontechnologies.com User: gcccgtm Pass: gcgm-4796! Port: 21