## Timeline - August launch
Week ending (Sat.)
ID | Task_Name | time axis 2013-11-09 to 2014-08-30
1 | Project Management Tasks
1.01 |  | Update Project Plan | x | x | x | N/A | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x
1.02 |  | Weekly Internal Beacon Project Meeting | x | x | x | N/A | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x
1.03 |  | Client Project Meeting | 2013-11-05 | 2013-11-12 | 2013-11-19 | N/A | 2013-12-03 | 2013-12-10 | N/A | N/A | N/A | N/A | 2013-01-14 | TBD | 2013-01-28 | 2013-02-04 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD
2 | Analysis and Project Approval Phase
2.01 |  | Project Kick-off Meeting | 2013-11-09: 2013-11-05
2.02 |  | Preliminary deliverables provided | 2013-12-21: 2013-12-13
2.03 |  | College feedback on all discussion topics and preliminary devilerables | 2014-01-25: 2014-01-25
2.04 |  | Final deliverables provided | 2014-02-01: 2014-01-31
2.05 |  | Analysis Phase Signoff/Approval from Client | 2014-02-08: 2014-02-07
3 | Information Architecture Revew Phase
3.01 |  | Client review and completion of content inventory/information architecture | bar: 2014-02-15 to 2014-04-05
3.02 |  | Final content inventory for both sites due from stakeholders | 2014-04-05: 2013-04-04
3 | Cascade Development Phase
3.01 |  | Template development | bar: 2014-02-15 to 2014-03-15
3.02 |  | Features development | bar: 2014-02-15 to 2014-03-15
3.03 |  | Cascade functionality | bar: 2014-02-15 to 2014-03-15
4 | Testing Phase
4.01 |  | Develop System Test Plan | bar: 2014-03-15
4.02 |  | Test Environment Setup | bar: 2014-03-15
4.03 |  | Perform System Testing | bar: 2014-03-15 to 2014-03-22
4.04 |  | System Testing Complete (Severity Level 1 & 2 CRs resolved) | 2014-03-22: 2014-03-22
4.05 |  | UAT Performed by Client | bar: 2014-03-29 to 2014-04-12
4.06 |  | Log Failure and Enhancement Change Requests (by Client) | 2014-04-12: 2014-04-11
4.07 |  | All Severity Level 1 & 2 Change Requests resolved | 2014-04-19: x; 2014-04-26: 2013-04-26
5 | Content Import and Integration Phase
5.01 |  | Site freeze | 2014-05-10: TBD
5.02 |  | Content import-- pages from old sites imported and saved in old site structure within Cascade (included in current budget) | bar: 2014-05-10 to 2014-05-24
5.03 |  | Content Integration-- Move imported pages of old site into new navigational schema and select site template (not included in current budget) | bar: 2014-05-24 to 2014-07-12
5.04 |  | Cascade user training | 2014-07-19: TBD
5.05 |  | College content owners review and edit content as needed | bar: 2014-07-19 to 2014-08-09
6 | Final Site Testing and Launch
6.01 |  | Final site testing (client and Beacon) | bar: 2014-08-16 to 2014-08-23
6.02 |  | Client approval for launch | 2014-08-23: TBD
6.03 |  | "Go Live" Date | 2014-08-30: TBD
6.04 |  | Production Release Verification | 2014-08-30: TBD
6.05 |  | Implementation Phase Signoff/Approval from Client | 2014-08-30: TBD
Key
Completed
Client tasks
Note on N6: Fowler, Annette: Prelim deliverables
Note on O6: Fowler, Annette: Flex week workshop
Note on P6: Fowler, Annette: Discuss final deliverables

## Client Action Items
# | Task | Responsible | Due | Status | Comments
1 | Formal project communication plan | Anne/Shari/Kerry | 11/19 (progress report) |  | Include location of public project documentation and option for feedback
2 | Determine members of college committee | All | 11/19 (progress report)
3 | Flex week workshop organization | Sue for Grossmont, Kerry for Cuyamaca, Anne will be a point person | 2014-01-25
4 | Provide August registration dates for each college to determine final launch date(s) | Jeff for Grossmont, Kerry for Cuyamaca | 2013-12-10
5 | Provide Grossmont graphical standards, if available, as reference for selection of 8-12 “standard” color options for bucket background colors | ? | 2013-12-03
6 | Arrange for meeting room for task force meetings | Debbie | 2013-11-12 | Complete

## Questions for College Committee
# | Section/Area | Question | Date Noted
1 | Faculty template | Would faculty members like to have the option to create an unlimited number of sub-pages in Cascade within their faculty profile? Would require Cascade user ids and training for those that would like to create those pages. | 2013-11-12
2 | Faculty template | Are there other sub-pages besides “Introduction” that should be included (and maintained) for every faculty member (i.e. “Resources”)? Note: links to external websites (like Blackboard or personal websites) could be included in left navigation for each faculty member, as needed. | 2013-11-12
3 | Faculty template | Should administration and/or staff members also have profile pages? | 2013-11-12
4 | Faculty template | Should the option for accordions and buckets be provided on faculty pages? | 2013-11-12
5 | Cascade | Should all content editors be able to create landing pages, or only standard two and three column pages? | 2013-11-12

## Beacon Action Items
# | Section/Page | Task | Status | Comments
1 | Design | Provide dimensions for home page banners and bucket thumbnail images so that image creation can be started by each college as soon as possible
2 | Faculty template | Build faculty listing, faculty detail and department landing pages in microsites
3 | Footer | Make footer a tad taller so that more links can be accommodated in the 3rd and 4th column. (add "Safety")
4 | Footer | Research: Can additional social media icons can be added by CMS admin and please confirm that accounts can be edited/updated by CMS admin
5 | Header | Change "Find People" label to "Quick Links" in header drop down. Add "Security" and "Accreditation" as drop down options. Confirm that a Cascade admin could add/remove other links.
6 | Top Navigation | Top navigation-- Dropdown menus - 2 versions - one with tier 3 and one with tier 3&4 (mega dropdown) | In progress
7 | Home page - Banner | Add ability to link banner images and "Read more" link in caption text to file, internal or external page. Each banner can have a different, but optional, link. Current "Apply" button functionality does not change.
8 | Home page - Banner | Full width slider - slider caption will have a Read More link (optional)
9 | Home page - Featured Image | Design controls for navigation between slides | In progress
10 | Home page - Featured Image | Ability to link image to file, internal or external page
11 | Home page - Featured Image | Looks like the number of featured images is unlimited in Cascade? Suggest limiting to 8 or so?
12 | Home page - Featured Image | Auto rotate images
13 | Interior | Design a system of 8-12 background colors for the buckets based on the color palates currently being used. | In progress
14 | Interior | Research: Would like to be able to use accordions and buckets on three column standard and landing pages.
15 | Interior | Research: Can we add ability to pick background color of buckets from set of 8-12 colors (TBD)

## References
Items | URL | Comment
Intranet site | http://intranet.gcccd.edu/website-steering/default.html
Grossmont mini site | http://grossmont.beacontest.com/default.html
Cuyamaca mini site | http://cuyamaca.beacontest.com/default.html
Original Cuyamaca designs | http://cmsc.gcccd.edu
Original Grossmont designs | http://cmsg.gcccd.edu