## Timeline - August launch
Week ending (Sat.)
ID | Task_Name | time axis 2013-11-09 to 2015-01-10
1 | Project Management Tasks
1.01 |  | Update Project Plan | x | x | x | N/A | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x
1.02 |  | Weekly Internal Beacon Project Meeting | x | x | x | N/A | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x
1.03 |  | Client Project Meeting | 2013-11-05 | 2013-11-12 | 2013-11-19 | N/A | 2013-12-03 | 2013-12-10 | N/A | N/A | N/A | N/A | 2013-01-14 | TBD | 2013-01-28 |  |  | 2014-02-19 | 2014-02-25 | 2014-03-04 | 2014-03-11 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD
1.04 |  | Cuyamaca committee mtg | 2013-12-14: 2013-12-11; 2014-01-25: TBD
1.05 |  | Grossmont committee mtg | 2013-12-21: 2013-12-16; 2014-01-25: TBD
2 | Analysis and Project Approval Phase
2.01 |  | Project Kick-off Meeting | 2013-11-09: 2013-11-05
2.02 |  | Preliminary deliverables provided | 2013-12-14: 2013-12-13
2.03 |  | Client feedback on all discussion topics and preliminary deliverables | 2014-03-01: 2014-02-28
2.04 |  | Final deliverables provided | 2014-03-08: 2014-03-07; 2014-03-15: 2014-03-10
2.05 |  | Faculty page feedback due from client | 2014-03-15: 2014-03-14
2.06 |  | Faculty addendum provided to client by Beacon | 2014-03-22: 2014-03-18
2.07 |  | Analysis Phase Signoff/Approval from Client | 2014-03-15: x; 2014-03-22: 2014-03-21
3 | Information Architecture Revew Phase
3.01 |  | Prelimindary content matrix and site hierarchy provided by Beacon | 2014-03-22: 2014-03-21
3.02 |  | Client review and completion of content inventory/information architecture | bar: 2014-03-29 to 2014-05-17
3.03 |  | Final content inventory for both sites due from stakeholders | 2014-05-17: 2014-05-16
3 | Cascade Development Phase
3.01 |  | Template development | bar: 2014-03-29 to 2014-04-26
3.02 |  | Features development | bar: 2014-03-29 to 2014-04-26
3.03 |  | Cascade functionality | bar: 2014-03-29 to 2014-04-26
4 | Testing Phase
4.01 |  | Develop System Test Plan | bar: 2014-04-26
4.02 |  | Test Environment Setup | bar: 2014-04-26
4.03 |  | Perform System Testing | bar: 2014-04-26 to 2014-05-03
4.04 |  | System Testing Complete (Severity Level 1 & 2 CRs resolved) | 2014-05-03: 2014-05-02
4.05 |  | UAT Performed by Client | bar: 2014-05-10 to 2014-05-24
4.06 |  | Log Failure and Enhancement Change Requests (by Client) | 2014-05-24: 2014-05-23
4.07 |  | All Severity Level 1 & 2 Change Requests resolved | 2014-05-31: x; 2014-06-07: 2014-06-06
5 | Content Import and Integration Phase
5.01 |  | Current site download/snapshot-- Content edited on live sites after this date needs to be documented and then updated by the client on the Cascade site after CMS training. | 2014-06-14: TBD
5.02 |  | Content import-- pages from old sites imported and saved in old site structure within Cascade (included in current budget) | bar: 2014-06-14 to 2014-06-28
5.03 |  | Content Integration-- Move imported pages of old site into new navigational schema and select site template (not included in current budget) | bar: 2014-06-28 to 2014-08-16
5.04 |  | Cascade user training | 2014-06-28: TBD; 2014-08-16: TBD
5.05 |  | College content owners review and edit content as needed | bar: 2014-08-23 to 2014-09-13
6 | Final Site Testing and Launch
6.01 |  | Final site testing (client and Beacon) | bar: 2014-09-20 to 2014-09-27
6.02 |  | Client approval for launch | 2014-09-27: TBD
6.03 |  | "Go Live" Date | 2014-10-04: TBD
6.04 |  | Production Release Verification | 2014-10-04: TBD
6.05 |  | Implementation Phase Signoff/Approval from Client | 2014-10-04: TBD
Key
Completed
Client tasks
Note on N6: Fowler, Annette: Prelim deliverables
Note on O6: Fowler, Annette: Flex week workshop
Note on S6: Fowler, Annette: noon-1pm PST, calendar discussion
Note on T6: Fowler, Annette: 9-10 am pst to discuss feedback for beacon
Note on U6: Fowler, Annette: Discuss feedback; 9-10:30 am
Note on V6: Fowler, Annette: Discuss final deliverables; 8-9 am
Note on AK42: Fowler, Annette: End of phase 1 contract

## Client Action Items
# | Task | Responsible | Due | Status | Beacon Comments | Client Comments
1 | Formal project communication plan | Anne/Shari/Kerry | 11/19 (progress report) | Complete | Include location of public project documentation and option for feedback
2 | Determine members of college committee | All | 11/19 (progress report) | Complete
3 | Flex week workshop organization | Sue for Grossmont, Kerry for Cuyamaca, Anne will be a point person | 2014-01-25 | Complete
4 | Provide August registration dates for each college to determine final launch date(s) | Jeff for Grossmont, Kerry for Cuyamaca | 2013-12-10 | Complete | Provided on 12/10 by Debbie: Summer 2014 ends Jul 31 Fall 2014 Registration: Jul 14 – Aug 15 Fall Semester starts Aug 18 (Professional Development Week for faculty is the week before)
5 | Provide Grossmont graphical standards, if available, as reference for selection of 8-12 “standard” color options for bucket background colors | ? | 2013-12-03 | Complete | Check with Jamie
6 | Arrange for meeting room for task force meetings | Debbie | 2013-11-12 | Complete
12 | Determine functionality and layout of audience pages (linked from tabs in top left corner of every page), if different from audience site maps described in requirements doc. | Committee | 2014-02-28 | Open
14 | Approve layout of departmental landing page in updated wireframes. | Committee | 2014-02-28 | Open
9 | Determine bucket design (background color vs. icons) | Committee |  | Complete | Buckets will have gray backgrounds with black headline text and no arrows or icons
10 | Approve mega menu design | Committee |  | Complete
11 | Approve footer design update | Committee |  | Complete
17 | Faculty Sub-pages - Each faculty member will have their own directory for storing files, etc? Will rights be only for that faculty member and sysadmins? Also related to this topic-- "Faculty use of Cascade for marketing vs. academic purposes" And "Committee will also discuss with Brian the need for an ASPX compatible server for hosting faculty academic sites (not Cascade), but that this is not included in the scope of the Cascade project." | Committee | N/A | Open | Beacon believe this is an internal discussion and not related to Cascade or the public site, therefore a decision is not require by 2/28. However, since it is a high priority topic for faculty, we recommend it is discussed further by the committee. Please let us know if any further info is needed.
18 | CLIENT REQUEST • Committee home page needs data definition to provide links to Charge & Composition PDF file, Meetings page, and Members page. Below this on the home page can be a WYSIWYG since each committee varies. | Debbie | 2014-02-28 | Open | Need to confirm that this request is feasible with current committee set up and that there are no other changes to Committee template required.
7 | Determine administrator priveldges for each college: • Can determine folders and pages that can be edited and/or viewed, what toolbar options can be seen in the editor, what types of documents/files can be uploaded, etc. • Administrators—District, Grossmont, Cuyamaca, All? • Types of User groups—page editors, page approvers, administrators, etc. • Needs to be documented by client before CMS client training | IT | Before content integration begins (May 2014) | Open
8 | Determine format of pages (HTML/PHP/ASP/ASPX): • Current district site is HTML and Cuyamaca and Grossmont are ASP • NOTE: server side include support on webserver will be required to accomplish current requirements regarding publishing | IT | Before final development begins (Feb 2014) | Open
16 | CLIENT REQUEST-- Faculty Detail page - Courses - link is defined by faculty? Most faculty won't know what to do with a WYSIWYG. They need a data definition to put their syllabus, assignments, textbook, etc. See Alicia.Munoz, Kathy.Kotowski, anniezuckerman, barbara.pescar. lyn.neylon, michael.campbell" | Rhonda/Kerry | 2014-02-28 | Open | Further information on this item with examples if changes to faculty template functionality is required
13 | CLIENT REQUEST-- Section 508 - Is there a way to make it more apparent what element is active when tabbing through a page? For instance, try tabbing through the GCCCD home page and choosing Quick Links or the navigation circles beneath the features images. “ | Rhonda/Kerry | 2014-02-28 | Open | Need feedback on screenshot provided
19 | • 3.0 Optional - Admissions Deadlines - this is JavaScript... can this be pasted into a WYSIWYG and work? We need a way to create pages that have JavaScript functionality besides what is built-in, in order to not be trapped in 2013. | Rhonda/Kerry | 2014-02-28 | Open | Need code to test

## Questions for College Committee
# | Section/Area | Question | Date Noted
1 | Faculty template | Would faculty members like to have the option to create an unlimited number of sub-pages in Cascade within their faculty profile? Would require Cascade user ids and training for those that would like to create those pages. | 2013-11-12
2 | Faculty template | Are there other sub-pages besides “Introduction” that should be included (and maintained) for every faculty member (i.e. “Resources”)? Note: links to external websites (like Blackboard or personal websites) could be included in left navigation for each faculty member, as needed. | 2013-11-12
3 | Faculty template | Should administration and/or staff members also have profile pages? | 2013-11-12
4 | Faculty template | Should the option for accordions and buckets be provided on faculty pages? | 2013-11-12
5 | Cascade | Should all content editors be able to create landing pages, or only standard two and three column pages? | 2013-11-12

## Beacon Action Items
# | Section/Page | Task | Status | Comments
16 | Calendar | Contact collegenet re: calendaring options | Complete | Feedback to be provided with final deliverables
17 | Calendar | Provide list of pros/cons between Google, Hannon Hill and R25 calendars | Complete
4 | Footer | Research: Can additional social media icons can be added by CMS admin and please confirm that accounts can be edited/updated by CMS admin | Complete | Confirmed, additional social media icons can be added by Admins. Which administrators should be added to allow editing these items?
5 | Header | Change "Find People" label to "Find:" in header drop down. Add "Security" and "Accreditation" as drop down options. Confirm that a Cascade admin could add/remove other links. | Complete
14 | Interior | Research: Would like to be able to use accordions and buckets on three column standard and landing pages. | Complete | See http://grossmont.beacontest.com/landing-3-col.html
15 | Interior | Research: Can we add ability to pick background color of buckets from set of 8-12 colors (TBD) | Complete | Not recommended by our designer. See "Screenshots" tab for how this might be displayed. Our designer notes that the different colors don't
18 | Interior | Add social media sharing icons to interior templates | Complete
1 | Design | Provide dimensions for home page banners and bucket thumbnail images so that image creation can be started by each college as soon as possible | Complete | 1158 x 563 – homepage slider 293 x 215 – homepage featurette 241 x 161 – Interior bucket spots
2 | Faculty template | Build faculty listing, faculty detail and department landing pages in microsites | Complete | http://cuyamaca.beacontest.com/faculty-staff/default.html http://grossmont.beacontest.com/faculty-staff/default.html
3 | Footer | Make footer a tad taller so that more links can be accommodated in the 3rd and 4th column. (add "Safety") | Complete | To be included in designs provided with preliminary deliverables
7 | Home page - Banner | Add ability "Read more" link in caption text to file, internal or external page. Each banner can have a different, but optional, link. Current "Apply" button functionality does not change. | Complete | In test - http://gcccd.beacontest.com, http://cuyamaca.beacontest.com, http://grossmont.beacontest.com/. Note, banner image link not recommended.
8 | Home page - Banner | Full width slider - slider caption will have a Read More link (optional) | Complete
11 | Home page - Featured Image | Looks like the number of featured images is unlimited in Cascade? Suggest limiting to 8 or so? | Complete | Recommend limiting to 8 slides
9 | Home page - Featured Image | Design controls for navigation between slides | Complete | To be included in designs provided with preliminary deliverables
10 | Home page - Featured Image | Ability to link image to file, internal or external page | Complete | In test - http://gcccd.beacontest.com, http://cuyamaca.beacontest.com, http://grossmont.beacontest.com/
12 | Home page - Featured Image | Auto rotate images | Complete | In test - http://gcccd.beacontest.com, http://cuyamaca.beacontest.com, http://grossmont.beacontest.com/
13 | Interior | Design a system of 8-12 background colors for the buckets based on the color palates currently being used. | Complete | To be included in designs provided with preliminary deliverables
6 | Top Navigation | Top navigation-- Dropdown menus - 2 versions - one with tier 3 and one with tier 3&4 (mega dropdown) | Complete | To be included in designs provided with preliminary deliverables
19 | http://cuyamaca.beacontest.com/future-students/default.html | The address in the footer should be a link to Maps & Directions | Complete
20 | http://cuyamaca.beacontest.com/current-students/technology-resources.html | Breadcrumbs should link back to home page | Complete
21 | /programs-departments/default.html | 3. This content totally out of place. They copied in one of the DSPS pages here, which should be linking to the whole DSPS site: http://www.cuyamaca.edu/dsps/ 4. DSPS High Tech Center should be an h3 and not smaller than the h2. Headers should be progressively smaller, the higher the number. | N/A | This is sample text. Final content will be determined during information architecture phase.
22 | /programs-departments/default.html | Link image as well as headline text | Complete
23 | Interior | Links in the footer should go to the pages already linked in the current Cuyamaca home page on Cascade Server. | N/A | This is sample text. Final content will be determined during information architecture phase.
24 | Accordian | Create sample page with this functionlaity: http://www.cuyamaca.edu/gd/class-desc.asp | In progress
25 | Header | Add show all button above accordian to open all items | Complete
26 | Header | Make sure logo has alt text and that it contains the full college name | Complete
27 | Header | Client thinks the blue being used on mini site doesn't match original design here: http://cmsc.gcccd.edu/admissions/sub-page.html and wants to know if black line can be added back in. | Complete
28 | Home | Make background for the featured area a gray gradient like the News and Events sections | Complete

## References
Items | URL | Comment
Intranet site | http://intranet.gcccd.edu/website-steering/default.html
Grossmont sample site | http://grossmont.beacontest.com/default.html
Cuyamaca sample site | http://cuyamaca.beacontest.com/default.html
Original Cuyamaca designs | http://cmsc.gcccd.edu
Original Grossmont designs | http://cmsg.gcccd.edu
FTP location for meeting recordings | Host: ftp.beacontechnologies.com User: gcccgtm Pass: gcgm-4796! Port: 21