## Timeline - August launch
Week ending (Sat.)
ID | Task_Name | time axis 2013-11-09 to 2014-08-30
1 | Project Management Tasks
1.01 |  | Update Project Plan | x | x | x | N/A | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x
1.02 |  | Weekly Internal Beacon Project Meeting | x | x | x | N/A | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x
1.03 |  | Client Project Meeting | 2013-11-05 | 2013-11-12 | 2013-11-19 | N/A | 2013-12-03 | 2013-12-10 | 2013-12-17 | N/A | N/A | 2013-01-07 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD
2 | Analysis and Project Approval Phase
2.01 |  | Project Kick-off Meeting | 2013-11-09: 2013-11-05
2.02 |  | Preliminary deliverables provided | 2013-12-14: 2013-12-13
2.03 |  | College feedback on all discussion topics and preliminary devilerables | 2013-12-21: 2013-12-20
2.04 |  | Final deliverables provided | 2013-12-28: 2013-12-27
2.05 |  | Analysis Phase Signoff/Approval from Client | 2014-01-11: 2014-01-10
3 | Information Architecture Revew Phase
3.01 |  | Client review and completion of content inventory/information architecture | bar: 2014-01-18 to 2014-03-08
3.02 |  | Final content inventory for both sites due from stakeholders | 2014-03-08: 2014-03-07
3 | Cascade Development Phase
3.01 |  | Template development | bar: 2014-01-18 to 2014-02-15
3.02 |  | Features development | bar: 2014-01-18 to 2014-02-15
3.03 |  | Cascade functionality | bar: 2014-01-18 to 2014-02-15
4 | Testing Phase
4.01 |  | Develop System Test Plan | bar: 2014-02-22
4.02 |  | Test Environment Setup | bar: 2014-02-22
4.03 |  | Perform System Testing | bar: 2014-02-22 to 2014-03-01
4.04 |  | System Testing Complete (Severity Level 1 & 2 CRs resolved) | 2014-03-01: 2014-02-28
4.05 |  | UAT Performed by Client | bar: 2014-03-08 to 2014-03-22
4.06 |  | Log Failure and Enhancement Change Requests (by Client) | 2014-03-22: 2013-03-21
4.07 |  | All Severity Level 1 & 2 Change Requests resolved | 2014-03-29: x; 2014-04-05: 2014-04-04
5 | Content Import and Integration Phase
5.01 |  | Site freeze | 2014-05-10: TBD
5.02 |  | Content import-- pages from old sites imported and saved in old site structure within Cascade (included in current budget) | bar: 2014-05-10 to 2014-05-24
5.03 |  | Content Integration-- Move imported pages of old site into new navigational schema and select site template (not included in current budget) | bar: 2014-05-24 to 2014-07-12
5.04 |  | Cascade user training | 2014-07-19: TBD
5.05 |  | College content owners review and edit content as needed | bar: 2014-07-19 to 2014-08-09
6 | Final Site Testing and Launch
6.01 |  | Final site testing (client and Beacon) | bar: 2014-08-16 to 2014-08-23
6.02 |  | Client approval for launch | 2014-08-23: TBD
6.03 |  | "Go Live" Date | 2014-08-30: TBD
6.04 |  | Production Release Verification | 2014-08-30: TBD
6.05 |  | Implementation Phase Signoff/Approval from Client | 2014-08-30: TBD
Key
Completed
Client tasks